## ETL_Tracker
UID | WBS | EMAIL SENT | TASK COMPLETION | STATUS | Task Name | Duration (Hrs) | Start | Finish | BaseLine Start | Resource Names | Team | Predecessors | Tag Status | Defect | Comments | Back up Resources | Start IST | Big3 Check | Cutover Change Required | Defect - cutover | Defect - cutover - Description | Cutover Change Status | Updated Resources | Base Line Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | #start | #issue | #done | There
5096 | WBS.2.1.4.1.1.4 | Y | Y | #done | MDG_C0098 - Execute Transform program for Materials - Classifications View | 1.22 | 2020-08-04 14:13 | 2020-08-04 15:26 | 2020-08-04 | ANJALI SINHA | DATA | 5090 | #done |  |  | ANJALI SINHA | 2020-08-04 23:43 | [7 empty] | 5090 - Complete | [11 empty] | FALSE | FALSE | TRUE | FALSE
8792 | WBS.2.1.4.1.1.9 | Y | Y | #start | Maintain XREF Values In BODS For Data Conversions - SCM | 0.12 | 2020-08-03 10:12 | 2020-08-03 10:19 | 2020-08-03 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2020-08-03 19:42 | [7 empty] | 36501 - Complete | [11 empty] | TRUE | FALSE | FALSE | FALSE
82567 | WBS.2.1.4.1.3.8 | Y | Y | #start | Maintain XREF Values In BODS For Data Conversions - EWM | 0.12 | 2020-08-03 10:12 | 2020-08-03 10:19 | 2020-08-03 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2020-08-03 19:42 | Material | [6 empty] | 36501 - Complete | [11 empty] | TRUE | FALSE | FALSE | FALSE
82574 | WBS.2.1.10.2.6.3 | Y | Y | Task Received | MC Task ¦ Create HDBODBC Connection And Validate For QA | 0.11 | 2020-08-03 10:12 | 2020-08-03 10:19 | 2020-08-03 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2020-08-03 19:42 | [7 empty] | 36501 - Complete | [14 empty] | FALSE
82575 | WBS.2.1.10.2.6.5 | Y | Y | Task Received | MC Task ¦ Sanity Testing of Job Execution In BODS QA | 0.2 | 2020-08-03 10:12 | 2020-08-03 10:24 | 2020-08-03 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2020-08-03 19:42 | [7 empty] | 36501 - Complete | [14 empty] | FALSE
3967 | WBS.2.1.10.2.6.10 | Y | Y | Task Received | Execute Extracts from Maintelligence for master data and non open item transaction data conversions | 0.38 | 2020-08-03 10:12 | 2020-08-03 10:34 | 2020-08-03 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2020-08-03 19:42 | [7 empty] | 93067 - Complete | [14 empty] | FALSE
3968 | WBS.2.1.10.2.6.11 | Y | Y | Task Received | Execute Extracts from AS8 (PTM) for master data and non open item transaction data conversions | 0.34 | 2020-08-03 10:12 | 2020-08-03 10:32 | 2020-08-03 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2020-08-03 19:42 | [7 empty] | 93067 - Complete | [14 empty] | FALSE
3966 | WBS.2.1.10.2.6.4 | Y | Y | Task Received | Execute Extracts from AS8 for master data and non open item transaction data conversions | 0.25 | 2020-08-03 10:12 | 2020-08-03 10:27 | 2020-08-03 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2020-08-03 19:42 | [7 empty] | 93067 - Complete | [14 empty] | FALSE
94411 | WBS.2.1.10.2.1.5 | Y | Y | Task Received | Execute Extracts from MP2 for master data and non open item transaction data conversions | 0.26 | 2020-08-03 10:12 | 2020-08-03 10:28 | 2020-08-03 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2020-08-03 19:42 | [6 empty] | 1 | 93067 - Complete | [14 empty] | FALSE
3964 | WBS.2.2.1.7.13.3 | Y | Y | Task Received | Execute Extracts from ECC for master data - confirm completed | 0.31 | 2020-08-03 10:12 | 2020-08-03 10:30 | 2020-08-03 | ANJALI SINHA | Data | 5231,10038,9091,81155 | #done |  |  | ANJALI SINHA | 2020-08-03 19:42 | [7 empty] | 5231 - Complete | 10038 - Complete | 9091 - Complete | 81155 - Complete | [11 empty] | FALSE
82569 |  | Y | Y | Task Received | Maintain XREF Values In BODS For Data Conversions - AC | 0 | 2020-08-03 11:18 | 2020-08-03 11:18 | 2020-08-03 | JASPREET SINGH | DATA | 4063 | #done |  |  | JASPREET SINGH | 2020-08-03 20:48 | [7 empty] | 4063 - Complete | [14 empty] | FALSE
82570 | WBS.2.1.10.2.6.1 | Y | Y | Task Received | Maintain XREF Values In BODS For Data Conversions - PTP | 0.04 | 2020-08-03 10:31 | 2020-08-03 10:33 | 2020-08-03 | JASPREET SINGH | DATA | 80788 | #done |  |  | JASPREET SINGH | 2020-08-03 20:01 | [7 empty] | 80788 - Complete | [14 empty] | FALSE
89984 | WBS.2.1.15.9.1.20 | Y | Y | Task Received | PTM_C0245 - Execute Preload - TAPPI ID conversion | 0.05 | 2020-08-03 12:26 | 2020-08-03 12:29 | 2020-08-03 | PRADEEP CHEEDALLA | DATA | 89985 | #done |  |  | PRADEEP CHEEDALLA | 2020-08-03 21:56 | [6 empty] | 1 | 89985 - Complete | [14 empty] | FALSE
89675 | WBS.2.1.8.2.2.2 | Y | Y | Task Received | Update Vendor cross reference and Vendor In-Scope | 1.82 | 2020-08-03 12:59 | 2020-08-03 14:48 | 2020-08-03 | ANJALI SINHA | DATA | 89679 | #done | 44378 |  | ANJALI SINHA | 2020-08-03 22:29 | Material | [6 empty] | 89679 - Complete | [14 empty] | FALSE