## ETL_Tracker
UID | WBS | EMAIL SENT | TASK COMPLETION | STATUS | Task Name | Duration (Hrs) | Start | Finish | BaseLine Start | Resource Names | Team | Predecessors | Tag Status | Defect | Comments | Back up Resources | Start IST | Big3 Check | Cutover Change Required | Defect - cutover | Defect - cutover - Description | Cutover Change Status | Updated Resources | Base Line Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Status to be updated | #start | #issue | #done | There
3967 | WBS.2.1.10.2.6.10 | Y | Y | Complete | Execute Extracts from Maintelligence for master data and non open item transaction data conversions | 0 | 2020-10-05 00:10 | 2020-10-05 00:31 | 2020-10-05 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2020-10-05 09:40 | [7 empty] | 1: 93067 - Complete | #done | FALSE | FALSE | TRUE | FALSE
3968 | WBS.2.1.10.2.6.11 | Y | Y | Complete | Execute Extracts from AS8 (PTM) for master data and non open item transaction data conversions | 0 | 2020-10-05 00:10 | 2020-10-05 00:30 | 2020-10-05 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2020-10-05 09:40 | [7 empty] | 1: 93067 - Complete | #done | FALSE | FALSE | TRUE | FALSE
3966 | WBS.2.1.10.2.6.4 | Y | Y | Complete | Execute Extracts from AS8 for master data and non open item transaction data conversions | 0 | 2020-10-05 00:10 | 2020-10-05 00:32 | 2020-10-05 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2020-10-05 09:40 | [7 empty] | 1: 93067 - Complete | #done | FALSE | FALSE | TRUE | FALSE
94411 | WBS.2.1.10.2.1.5 | Y | Y | Complete | Execute Extracts from MP2 for master data and non open item transaction data conversions | 0 | 2020-10-05 00:10 | 2020-10-05 00:30 | 2020-10-05 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2020-10-05 09:40 | [6 empty] | 1 | 1: 93067 - Complete | #done | FALSE | FALSE | TRUE | FALSE
3964 | WBS.2.2.1.7.13.3 | Y | Y | Complete | Execute Extracts from ECC for master data - confirm completed | 0 | 2020-10-05 00:25 | 2020-10-05 00:29 | 2020-10-05 | ANJALI SINHA | Data | 93067 | #done |  |  | ANJALI SINHA | 2020-10-05 09:55 | [7 empty] | 1: 93067 - Complete | #done | FALSE | FALSE | TRUE | FALSE
82561 | WBS.2.1.4.1.1.4 | Y | Y | Complete | Create XREF Table Indices In HANA DB | 0.11 | 2020-10-05 06:30 | 2020-10-05 06:37 | 2020-10-05 | ANKIT AGARWAL | DATA | 36501 | #done |  |  | ANKIT AGARWAL | 2020-10-05 16:00 | [7 empty] | 1: 36501 - Complete | #done | FALSE | FALSE | TRUE | FALSE
82566 | WBS.2.1.4.1.1.9 | Y | N | In-Progress | Maintain XREF Values In BODS For Data Conversions - SCM | 0.5 | 2020-10-05 06:46 | 2020-10-05 07:16 | 2020-10-05 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2020-10-05 16:16 | [7 empty] | 1: 36501 - Complete | #done | FALSE | FALSE | TRUE | FALSE
82567 | WBS.2.1.4.1.3.8 | Y | N | In-Progress | Maintain XREF Values In BODS For Data Conversions - EWM | 0.5 | 2020-10-05 06:46 | 2020-10-05 07:16 | 2020-10-05 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2020-10-05 16:16 | Material | [6 empty] | 1: 36501 - Complete | #done | FALSE | FALSE | TRUE | FALSE
82574 | WBS.2.1.10.2.6.3 | Y | N | In-Progress | MC Task ¦ Create HDBODBC Connection And Validate For QA | 0.5 | 2020-10-05 06:46 | 2020-10-05 07:16 | 2020-10-05 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2020-10-05 16:16 | [7 empty] | 1: 36501 - Complete | #done | FALSE | FALSE | TRUE | FALSE
82575 | WBS.2.1.10.2.6.5 | Y | N | In-Progress | MC Task ¦ Sanity Testing of Job Execution In BODS QA | 0.5 | 2020-10-05 06:46 | 2020-10-05 07:16 | 2020-10-05 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2020-10-05 16:16 | [7 empty] | 1: 36501 - Complete | #done | FALSE | FALSE | TRUE | FALSE
82569 |  | Y | N | In-Progress | Maintain XREF Values In BODS For Data Conversions - AC | 0.5 | 2020-10-05 06:46 | 2020-10-05 07:16 | 2020-10-05 | JASPREET SINGH | DATA | 4063 | #done |  |  | JASPREET SINGH | 2020-10-05 16:16 | [7 empty] | 1: 4063 - Complete | #done | FALSE | FALSE | TRUE | FALSE
82570 | WBS.2.1.10.2.6.1 | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - PTP | 0.5 | 2020-10-05 06:49 | 2020-10-05 07:19 | 2020-10-05 | JASPREET SINGH | DATA | 80788 | #done |  |  | JASPREET SINGH | 2020-10-05 16:19 | [7 empty] | 1: 80788 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
89984 | WBS.2.1.15.9.1.20 | N | N | Planned | PTM_C0245 - Execute Preload - TAPPI ID conversion | 2 | 2020-10-05 07:19 | 2020-10-05 09:19 | 2020-10-05 | PRADEEP CHEEDALLA | DATA | 89985 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-05 16:49 | [6 empty] | 1 | 1: 89985 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
89675 | WBS.2.1.8.2.2.2 | N | N | Planned | Update Vendor cross reference and Vendor In-Scope | 2 | 2020-10-05 08:49 | 2020-10-05 10:49 | 2020-10-05 | ANJALI SINHA | DATA | 89679 | #done |  |  | ANJALI SINHA | 2020-10-05 18:19 | Material | [6 empty] | 1: 89679 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
82565 | WBS.2.1.4.1.1.5 | N | N | Planned | MDG_C0098 - Maintain XREF Values In BODS For Procured Materials Conversion | 0.5 | 2020-10-05 08:49 | 2020-10-05 09:19 | 2020-10-05 | JASPREET SINGH | DATA | 9125 | #done |  |  | JASPREET SINGH | 2020-10-05 18:19 | [7 empty] | 1: 9125 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
89674 | WBS.2.1.4.1.1.11 | N | N | Planned | Update Material cross reference and In-Scope tables | 1 | 2020-10-05 08:49 | 2020-10-05 09:49 | 2020-10-05 | DEEPA SAW | DATA | 36501,9125 | #done |  |  | DEEPA SAW | 2020-10-05 18:19 | [7 empty] | 1: 36501 - Complete; 2: 9125 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
89982 | WBS.2.1.8.2.2.1 | N | N | Planned | PTM_C0245 - Execute Load program - TAPPI ID conversion | 3 | 2020-10-05 09:34 | 2020-10-05 12:34 | 2020-10-05 | ANURAG ANAND | DATA | 89983 | Yet to receive |  |  | ANURAG ANAND | 2020-10-05 19:04 | Material | [6 empty] | 1: 89983 - Planned | #done | FALSE | FALSE | FALSE | FALSE
5233 | WBS.2.1.9.29.1.3 | N | N | Planned | PTP_C0001 - Execute Transform program - Convert PTP contracts | 2 | 2020-10-05 10:49 | 2020-10-05 12:49 | 2020-10-05 | ANKIT AGARWAL | DATA | 89679,89675,3964,82570 | #done |  |  | Ishaq | 2020-10-05 20:19 | [6 empty] | 1 | 1: 89679 - In-Progress; 2: 89675 - Planned; 3: 3964 - Complete; 4: 82570 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5243 | WBS.2.1.8.1.1.58 | N | N | Planned | PTP_C0008 - Execute Transform program - Convert Purchase Info Record - ECC | 1 | 2020-10-05 10:49 | 2020-10-05 11:49 | 2020-10-05 | ANJALI SINHA | DATA | 89675,89679,3964,82570 | #done |  |  | ANJALI SINHA | 2020-10-05 20:19 | Material | [6 empty] | 1: 89675 - Planned; 2: 89679 - In-Progress; 3: 3964 - Complete; 4: 82570 - Planned | #done | FALSE | FALSE | TRUE | FALSE
95364 | WBS.2.2.1.7.16.5 | N | N | Planned | PTP_C0008 - To perform deletion of FG PIRs - Convert Purchase Info Record - ECC | 1 | 2020-10-05 12:49 | 2020-10-05 13:49 | 2020-10-05 | ANJALI SINHA | DATA | 95365 | #done |  |  | ANJALI SINHA | 2020-10-05 22:19 | [7 empty] | 1: 95365 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5235 | WBS.2.1.15.7.1.2 | N | N | Planned | PTP_C0001 - Execute Load program - Contracts (Before load, manually create one contract but do not save) | 3 | 2020-10-05 14:49 | 2020-10-06 01:49 | 2020-10-06 | PHANI GHANTASALA | DATA | 5234 | #done |  |  | PHANI GHANTASALA | 2020-10-06 00:19 | [7 empty] | 1: 5234 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10137 | WBS.2.1.15.17.1.8 | N | N | Planned | MDG_C0098 - Execute DQ job to identify in-scope AS8 Procured materials | 4 | 2020-10-05 09:02 | 2020-10-05 13:02 | 2020-10-05 | PRADEEP CHEEDALLA | DATA | 4229 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-05 18:32 | [7 empty] | 1: 4229 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5084 | WBS.2.1.10.2.6.8 | N | N | Planned | MDG_C0098 - Execute Transform program for AS8 Procured materials | 4 | 2020-10-05 09:02 | 2020-10-05 13:02 | 2020-10-05 | DEEPA SAW | DATA | 4229 | #done |  |  | DEEPA SAW | 2020-10-05 18:32 | [7 empty] | 1: 4229 - Planned | #done | FALSE | FALSE | TRUE | FALSE
9174 | WBS.2.2.1.7.13.22 | N | N | Planned | MDG_C0098 - Execute Preload for SPECS semi-finished materials manual load file | 3 | 2020-10-05 15:00 | 2020-10-06 02:00 | 2020-10-06 | PRADEEP CHEEDALLA | Data | 3976,9851,9852,4229 | #done |  |  | Aarthi | 2020-10-06 00:30 | [7 empty] | 1: 3976 - In-Progress; 2: 9851 - Planned; 3: 9852 - Planned; 4: 4229 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90888 | WBS.2.2.1.7.13.24 | N | N | Planned | MDG_C0098 - Execute Preload for ZUNB materials manual load file | 2 | 2020-10-05 09:19 | 2020-10-05 11:19 | 2020-10-05 | PRADEEP CHEEDALLA | Data | 90886,90887,3976,4229 | #done |  |  | Aarthi | 2020-10-05 18:49 | [7 empty] | 1: 90886 - In-Progress; 2: 90887 - Planned; 3: 3976 - In-Progress; 4: 4229 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92780 | WBS.2.1.15.23.1.1 | N | N | Planned | Execute Preload ITR_C0016.1 - Convert Functional Locations - MP2 | 1 | 2020-10-05 10:47 | 2020-10-05 11:47 | 2020-10-05 | JASPREET SINGH | DATA | 92781,5782 | #done |  |  | JASPREET SINGH | 2020-10-05 20:17 | [6 empty] | 1 | 1: 92781 - In-Progress; 2: 5782 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5390 | WBS.2.1.15.20.1.1 | N | N | Planned | ITR_C0016 - Execute Preload - Convert Functional Locations - AS8 | 1 | 2020-10-05 10:47 | 2020-10-05 11:47 | 2020-10-05 | JASPREET SINGH | DATA | 5782 | #done |  |  | JASPREET SINGH | 2020-10-05 20:17 | [6 empty] | 1 | 1: 5782 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5387 | WBS.2.1.15.6.1.4 | N | N | Planned | ITR_C0064 - Execute Load program - Convert Code And Code Groups | 1 | 2020-10-05 12:17 | 2020-10-05 13:17 | 2020-10-05 | VENKATESH GANESHAN | DATA | 4091,3995 | #done |  |  | VENKATESH GANESHAN | 2020-10-05 21:47 | [6 empty] | 1 | 1: 4091 - Planned; 2: 3995 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
5381 | WBS.2.1.15.15.1.12 | N | N | Planned | ITR_C0070 - Execute Load program - Convert Characteristics - AS8 and MP2 | 1 | 2020-10-05 12:17 | 2020-10-05 13:17 | 2020-10-05 | ANURAG ANAND | DATA | 3992,4091 | #done |  |  | ANURAG ANAND | 2020-10-05 21:47 | [7 empty] | 1: 3992 - In-Progress; 2: 4091 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10116 | WBS.2.1.15.8.1.4 | N | N | Planned | PTM_C0079 - Execute transformation for Work Center Conversion | 1 | 2020-10-05 12:04 | 2020-10-05 13:04 | 2020-10-05 | ANURAG ANAND | DATA | 89610,92229,92244,93067,91838,4667,94433,94432,96559 | #done |  |  | ANURAG ANAND | 2020-10-05 21:34 | [7 empty] | 89610 - Planned | 92229 - Planned | 92244 - Planned | 93067 - Complete | 91838 - Planned | 4667 - Planned | 94433 - Planned | 94432 - Planned | 96559 - Planned |  |  |  | #done | FALSE | FALSE | TRUE | FALSE
83323 | WBS.2.2.1.7.13.23 | N | N | Planned | MDG_C0098 - Generate Preload Validation report - SPECS semi finished material load file (all views) | 2 | 2020-10-06 02:00 | 2020-10-06 04:00 | 2020-10-06 | PRADEEP CHEEDALLA | Data | 9174 | #done |  |  | Aarthi | 2020-10-06 11:30 | [7 empty] | 1: 9174 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10138 | WBS.2.1.9.11.1.1 | N | N | Planned | MDG_C0098 - Compare DQ and ETL filtered in-scope AS8 Procured Materials and analyze/report differences | 3 | 2020-10-05 13:02 | 2020-10-05 16:02 | 2020-10-05 | PRADEEP CHEEDALLA | DATA | 10137,5084 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-05 22:32 | [7 empty] | 1: 10137 - Planned; 2: 5084 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10492 | WBS.2.1.9.6.1.2 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Basic View | 1 | 2020-10-05 13:02 | 2020-10-05 14:02 | 2020-10-05 | DEEPA SAW | DATA | 5084 | #done |  |  | DEEPA SAW | 2020-10-05 22:32 | Customer | [6 empty] | 1: 5084 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10493 |  | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Purchasing/MRP View | 1 | 2020-10-05 14:02 | 2020-10-05 15:02 | 2020-10-05 | DEEPA SAW | DATA | 10492 | #done |  |  | DEEPA SAW | 2020-10-05 23:32 | Material | [6 empty] | 1: 10492 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5384 | WBS.2.1.15.15.1.9 | N | N | Planned | ITR_C0069 - Execute Load program - Convert Classes - AS8 and MP2 | 1 | 2020-10-05 13:47 | 2020-10-05 14:47 | 2020-10-05 | ANURAG ANAND | DATA | 5382 | #done |  |  | ANURAG ANAND | 2020-10-05 23:17 | [7 empty] | 1: 5382 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10494 | WBS.2.1.10.2.6.6 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Accounting view | 1 | 2020-10-05 15:02 | 2020-10-05 16:02 | 2020-10-05 | DEEPA SAW | DATA | 10493 | #done |  |  | DEEPA SAW | 2020-10-06 00:32 | [7 empty] | 1: 10493 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10495 | WBS.2.1.10.2.6.7 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Storage view | 1 | 2020-10-05 16:02 | 2020-10-06 01:02 | 2020-10-06 | DEEPA SAW | DATA | 10494 | #done |  |  | DEEPA SAW | 2020-10-06 01:32 | [7 empty] | 1: 10494 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90055 | WBS.2.1.8.1.1.23 | N | N | Planned | Turn OFF DRFOUT, Turn ON Change Pointers for CLFMAS, MATMAS, MATQM in MDG | 0.5 | 2020-10-06 07:45 | 2020-10-06 08:15 | 2020-10-06 | PHANI GHANTASALA | DATA | 90082 | #done |  |  | PHANI GHANTASALA | 2020-10-06 17:15 | Material | [6 empty] | 1: 90082 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92778 | WBS.2.1.15.19.1.1 | N | N | Planned | Execute Load ITR_C0016.1 - Convert Functional Locations - MP2 | 3 | 2020-10-05 13:47 | 2020-10-05 16:47 | 2020-10-05 | JASPREET SINGH | DATA | 92779 | #done |  |  | JASPREET SINGH | 2020-10-05 23:17 | [7 empty] | 1: 92779 - Planned | #done | FALSE | FALSE | TRUE | FALSE
83325 | WBS.2.1.9.1.1.2 | N | N | Planned | Execute load for SPECS semi-finished materials manual load file (Including ZSOURCE characteristic) | 2.5 | 2020-10-06 08:15 | 2020-10-06 10:45 | 2020-10-06 | ANURAG ANAND | DATA | 90055,90054,90067,10371,92829 | #done |  |  | ANURAG ANAND | 2020-10-06 17:45 | [7 empty] | 1: 90055 - Planned; 2: 90054 - Planned; 3: 90067 - Planned; 4: 10371 - Planned; 5: 92829 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90890 | WBS.2.1.9.12.1.1 | N | N | Planned | MDG_C0098 - Execute load for ZUNB materials (Including ZSOURCE characteristic) | 2 | 2020-10-06 08:15 | 2020-10-06 10:15 | 2020-10-06 | ANURAG ANAND | DATA | 90889,90055,90054,90067,10371,92829 | #done |  |  | ANURAG ANAND | 2020-10-06 17:45 | [7 empty] | 1: 90889 - Planned; 2: 90055 - Planned; 3: 90054 - Planned; 4: 90067 - Planned; 5: 10371 - Planned; 6: 92829 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5090 | WBS.2.1.8.1.1.4 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Basic View | 2 | 2020-10-06 08:15 | 2020-10-06 10:15 | 2020-10-06 | DEBRAJ PAL | DATA | 90055,90054,10425,92114,92115,92829 | #done |  |  | DEBRAJ PAL | 2020-10-06 17:45 | Material | [6 empty] | 1: 90055 - Planned; 2: 90054 - Planned; 3: 10425 - Planned; 4: 92114 - Planned; 5: 92115 - Planned; 6: 92829 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10496 | WBS.2.1.8.1.1.5 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Sales View | 1 | 2020-10-06 01:02 | 2020-10-06 02:02 | 2020-10-06 | DEEPA SAW | DATA | 10495 | #done |  |  | DEEPA SAW | 2020-10-06 10:32 | Material | [6 empty] | 1: 10495 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10498 | WBS.2.2.1.7.13.20 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Basic View | 2 | 2020-10-06 10:15 | 2020-10-06 12:15 | 2020-10-06 | ANJALI SINHA | Data | 5090 | #done |  |  | ANJALI SINHA | 2020-10-06 19:45 | [7 empty] | 1: 5090 - Planned | #done | FALSE | FALSE | TRUE | FALSE
8807 | WBS.2.1.15.25.1.1 | N | N | Planned | ITR_C0030 - Execute Transformation program - Convert Functional Location Classification Values – AS8 | 2 | 2020-10-06 08:30 | 2020-10-06 10:30 | 2020-10-06 | ANJALI SINHA | DATA | 5385,5393,3966,82569 | #done |  |  | ANJALI SINHA | 2020-10-06 18:00 | [7 empty] | 1: 5385 - Planned; 2: 5393 - Planned; 3: 3966 - Complete; 4: 82569 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
5096 | WBS.2.1.9.14.1.1 | N | N | Planned | MDG_C0098 - Execute Transform program for Materials - Classifications View | 3 | 2020-10-06 10:15 | 2020-10-06 13:15 | 2020-10-06 | ANJALI SINHA | DATA | 5090 | #done |  |  | Krishna | 2020-10-06 19:45 | [7 empty] | 1: 5090 - Planned | #done | FALSE | FALSE | TRUE | FALSE
83324 | WBS.2.2.1.7.13.19 | N | N | Planned | Generate Post Load Validation report - SPECS semi-finished materials load file | 4 | 2020-10-06 10:45 | 2020-10-06 14:45 | 2020-10-06 | PRADEEP CHEEDALLA | Data | 83325 | #done |  |  | Aarthi | 2020-10-06 20:15 | [7 empty] | 1: 83325 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5392 | WBS.2.1.8.2.1.22 | N | N | Planned | ITR_C0016 - Execute Load program - Convert Functional Locations - AS8 | 5 | 2020-10-05 16:47 | 2020-10-06 05:47 | 2020-10-06 | JASPREET SINGH | DATA | 5391,92778 | #done |  |  | JASPREET SINGH | 2020-10-06 02:17 | Material | [6 empty] | 1: 5391 - Planned; 2: 92778 - Planned | #done | FALSE | FALSE | TRUE | FALSE
9148 | WBS.2.1.9.6.1.3 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Plant, MRP, Purchasing & Quality (MRO) | 4 | 2020-10-06 10:15 | 2020-10-06 14:15 | 2020-10-06 | DEBRAJ PAL | DATA | 5090,10418 | #done |  |  | DEBRAJ PAL | 2020-10-06 19:45 | [7 empty] | 1: 5090 - Planned; 2: 10418 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92785 | WBS.2.1.9.30.1.3 | N | N | Planned | Execute Preload ITR_C0018.1 - Convert equipment – MP2 | 1 | 2020-10-06 01:00 | 2020-10-06 02:00 | 2020-10-06 | VENKATESH GANESHAN | DATA | 92784,92777 | #done |  |  | VENKATESH GANESHAN | 2020-10-06 10:30 | [7 empty] | 1: 92784 - In-Progress; 2: 92777 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
10118 | WBS.2.1.15.21.1.2 | N | N | Planned | PTM_C0079 - Execute Smoke test load for Work Center Conversion | 1 | 2020-10-06 10:32 | 2020-10-06 11:32 | 2020-10-06 | ANURAG ANAND | DATA | 89613,7913 | #done |  |  | ANURAG ANAND | 2020-10-06 20:02 | [6 empty] | 1 | 1: 89613 - Planned; 2: 7913 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
10526 | WBS.2.1.13.1.1.8 | N | N | Planned | MDG_C0098 - Generate Preload Validation report - Procured materials - Classification view | 1 | 2020-10-06 13:15 | 2020-10-06 14:15 | 2020-10-06 | ANJALI SINHA | DATA | 5096 | #done |  |  | Krishna | 2020-10-06 22:45 | Vendor | [6 empty] | 1: 5096 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5405 | WBS.2.1.9.26.1.4 | N | N | Planned | ITR_C0071 - Execute Transform program - Convert Documents | 2 | 2020-10-06 08:30 | 2020-10-06 10:30 | 2020-10-06 | ANKIT AGARWAL | DATA | 5393,3966,82569,90491,94411 | #done |  |  | Ishaq | 2020-10-06 18:00 | [7 empty] | 1: 5393 - Planned; 2: 3966 - Complete; 3: 82569 - In-Progress; 4: 90491 - In-Progress; 5: 94411 - Complete | #done | FALSE | FALSE | TRUE | FALSE
92787 | WBS.2.1.9.8.1.10 | N | N | Planned | Execute Load ITR_C0018.1 - Convert equipment – MP2 | 1 | 2020-10-06 08:00 | 2020-10-06 09:00 | 2020-10-06 | VENKATESH GANESHAN | DATA | 92786 | #done |  |  | VENKATESH GANESHAN | 2020-10-06 17:30 | [7 empty] | 1: 92786 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82903 | WBS.2.1.15.16.1.8 | N | N | Planned | ITR_C0038 - Execute Transform program - Convert Task Lists – Functional Location Conversion - PTM | 2 | 2020-10-06 08:30 | 2020-10-06 10:30 | 2020-10-06 | ANKIT AGARWAL | DATA | 5393,3968,82569 | #done |  |  | ANKIT AGARWAL | 2020-10-06 18:00 | [7 empty] | 1: 5393 - Planned; 2: 3968 - Complete; 3: 82569 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
92806 | WBS.2.1.9.28.1.3 | N | N | Planned | Execute Preload ITR_C0065 - Convert Documents (Document Management System) - MP2 | 1 | 2020-10-06 11:00 | 2020-10-06 12:00 | 2020-10-06 | ANKIT AGARWAL | DATA | 94411,92777,92788 | #done |  |  | ANKIT AGARWAL | 2020-10-06 20:30 | [7 empty] | 1: 94411 - Complete; 2: 92777 - Planned; 3: 92788 - Planned | #done | FALSE | FALSE | TRUE | FALSE
9149 | WBS.2.1.10.2.6.2 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Accounting/Costing Views | 4 | 2020-10-06 14:15 | 2020-10-07 02:15 | 2020-10-07 | DEBRAJ PAL | DATA | 9148,10412 | #done |  |  | DEBRAJ PAL | 2020-10-06 23:45 | Material | [6 empty] | 1: 9148 - Planned; 2: 10412 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5427 | WBS.2.1.15.26.1.3 | N | N | Planned | ITR_C0055 - Execute Transform program - Convert Measuring Points (with catalogs) – Maintelligence | 2 | 2020-10-06 08:30 | 2020-10-06 10:30 | 2020-10-06 | JASPREET SINGH | DATA | 5382,5388,5393,3967,82569 | Yet to receive |  |  | Soham Saha | 2020-10-06 18:00 | [6 empty] | 1 | 1: 5382 - Planned; 2: 5388 - Planned; 3: 5393 - Planned; 4: 3967 - Complete; 5: 82569 - In-Progress | #done | FALSE | FALSE | FALSE | FALSE
90767 | WBS.2.1.15.17.1.8 | N | N | Planned | MDG_C0098 - Execute Preload for SPECS extension semi-finished materials and generate report | 2.5 | 2020-10-06 15:45 | 2020-10-07 02:15 | 2020-10-07 | PRADEEP CHEEDALLA | DATA | 9186,90768 | #done |  |  | Aarthi | 2020-10-07 01:15 | Material | [6 empty] | 1: 9186 - Planned; 2: 90768 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10499 | WBS.2.2.1.7.13.5 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Plant/Purchasing & Accounting/Costing Views | 3 | 2020-10-07 02:15 | 2020-10-07 05:15 | 2020-10-07 | ANJALI SINHA | Data | 9148,9149 | #done |  |  | ANJALI SINHA | 2020-10-07 11:45 | [7 empty] | 1: 9148 - Planned; 2: 9149 - Planned | #done | FALSE | FALSE | TRUE | FALSE
9150 | WBS.2.1.9.1.1.4 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Storage View | 4 | 2020-10-07 02:15 | 2020-10-07 06:15 | 2020-10-07 | DEBRAJ PAL | DATA | 9149,10306 | #done |  |  | DEBRAJ PAL | 2020-10-07 11:45 | [7 empty] | 1: 9149 - Planned; 2: 10306 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5177 | WBS.2.1.15.21.1.4 | N | N | Planned | PTM_C0079 - Execute Load program - PPDS Convert Work Centers | 2 | 2020-10-06 12:32 | 2020-10-06 14:32 | 2020-10-06 | ANURAG ANAND | DATA | 89612,36996,4667,94433,94432,96559 | #done |  |  | ANURAG ANAND | 2020-10-06 22:02 | [6 empty] | 1 | 1: 89612 - Planned; 2: 36996 - Planned; 3: 4667 - Planned; 4: 94433 - Planned; 5: 94432 - Planned; 6: 96559 - Planned | #done | FALSE | FALSE | TRUE | FALSE
9151 | WBS.2.1.15.11.1.1 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Sales View | 3 | 2020-10-07 06:15 | 2020-10-07 09:15 | 2020-10-07 | DEBRAJ PAL | DATA | 9150,10431 | #done |  |  | DEBRAJ PAL | 2020-10-07 15:45 | [7 empty] | 1: 9150 - Planned; 2: 10431 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10501 | WBS.2.1.9.10.1.4 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Storage View | 2 | 2020-10-07 06:15 | 2020-10-07 08:15 | 2020-10-07 | ANJALI SINHA | DATA | 9150 | #done |  |  | ANJALI SINHA | 2020-10-07 15:45 | [7 empty] | 1: 9150 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82901 | WBS.2.1.15.25.1.3 | N | N | Planned | ITR_C0038 - Execute Load program - Convert Task Lists – Functional Location Conversion - PTM | 1 | 2020-10-06 11:00 | 2020-10-06 12:00 | 2020-10-06 | DEBRAJ PAL | DATA | 82902 | #done |  |  | DEBRAJ PAL | 2020-10-06 20:30 | [7 empty] | 1: 82902 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5440 | WBS.2.1.15.24.1.1 | N | N | Planned | ITR_C0030 - Execute Load program - Convert Functional Location Classification Values – AS8 | 2 | 2020-10-06 11:00 | 2020-10-06 13:00 | 2020-10-06 | VENKATESH GANESHAN | DATA | 8808 | #done |  |  | VENKATESH GANESHAN | 2020-10-06 20:30 | [6 empty] | 1 | 1: 8808 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90765 | WBS.2.1.9.10.1.2 | N | N | Planned | Execute load for SPECS extension semi-finished materials manual load file (Including ZSOURCE characteristic) MDG_C0098 | 3 | 2020-10-07 07:00 | 2020-10-07 10:00 | 2020-10-07 | ANURAG ANAND | DATA | 90766 | #done |  |  | ANURAG ANAND | 2020-10-07 16:30 | [7 empty] | 1: 90766 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5407 | WBS.2.2.1.7.13.15 | N | N | Planned | ITR_C0071 - Execute Load program - Convert Documents | 2 | 2020-10-06 11:30 | 2020-10-06 13:30 | 2020-10-06 | VENKATESH GANESHAN | Data | 5406 | #done |  |  | VENKATESH GANESHAN | 2020-10-06 21:00 | [7 empty] | 1: 5406 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90050 | WBS.2.1.8.1.1.46 | N | N | Planned | Change BOM partner profile to collect mode in MDG | 0.25 | 2020-10-08 07:00 | 2020-10-08 07:15 | 2020-10-08 | PHANI GHANTASALA | DATA | 9799,10111 | #done |  |  | PHANI GHANTASALA | 2020-10-08 16:30 | Material | [6 empty] | 1: 9799 - Planned; 2: 10111 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92808 | WBS.2.1.15.18.1.3 | N | N | Planned | Execute Load ITR_C0065 - Convert Documents (Document Management System) - MP2 | 1 | 2020-10-06 12:45 | 2020-10-06 13:45 | 2020-10-06 | VENKATESH GANESHAN | DATA | 92807 | #done |  |  | VENKATESH GANESHAN | 2020-10-06 22:15 | [6 empty] | 1 | 1: 92807 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10502 | WBS.2.1.15.12.1.1 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Sales View | 2 | 2020-10-07 09:15 | 2020-10-07 11:15 | 2020-10-07 | ANJALI SINHA | DATA | 9151 | Yet to receive |  |  | ANJALI SINHA | 2020-10-07 18:45 | [7 empty] | 1: 9151 - Planned | #done | FALSE | FALSE | FALSE | FALSE
9928 | WBS.2.1.8.1.1.15 | N | N | Planned | MDG_C0098 - Generate In-Scope list and AS8 / S/4HANA material Xref and upload to SharePoint | 1 | 2020-10-07 09:15 | 2020-10-07 10:15 | 2020-10-07 | DEEPA SAW | DATA | 9151 | Yet to receive |  |  | DEEPA SAW | 2020-10-07 18:45 | Material | [6 empty] | 1: 9151 - Planned | #done | FALSE | FALSE | FALSE | FALSE
5100 | WBS.2.1.8.1.1.16 | N | N | Planned | MDG_C0098 - Execute Load in MDG - Materials - Classification View (ECC & AS8) | 4.5 | 2020-10-07 09:15 | 2020-10-07 13:45 | 2020-10-07 | ANJALI SINHA | DATA | 10423,9151 | #done |  |  | Krishna | 2020-10-07 18:45 | Material | [6 empty] | 1: 10423 - Planned; 2: 9151 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10120 | WBS.2.2.1.7.13.16 | N | N | Planned | PTM_C0079 - Execute load for Work Center Hierarchy | 2 | 2020-10-06 16:32 | 2020-10-07 02:32 | 2020-10-07 | ANURAG ANAND | Data | 89619 | #done |  |  | ANURAG ANAND | 2020-10-07 02:02 | [7 empty] | 1: 89619 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5122 | WBS.2.1.9.15.1.1 | N | N | Planned | Replicate Materials Quality View from MDG to S/4HANA | 0.5 | 2020-10-08 07:45 | 2020-10-08 08:15 | 2020-10-08 | PHANI GHANTASALA | DATA | 5121,10413 | #done |  |  | PHANI GHANTASALA | 2020-10-08 17:15 | [7 empty] | 1: 5121 - Planned; 2: 10413 - Planned | #done | FALSE | FALSE | TRUE | FALSE
95508 | WBS.2.2.1.7.16.5 | N | N | Planned | Execute Transform program - PTM_C0094 Convert Setup groups / Setup Matrix | 4 | 2020-10-06 18:02 | 2020-10-07 06:02 | 2020-10-07 | PRADEEP CHEEDALLA | DATA | 95509,95510 | #done |  |  | Ishaq/Krishna | 2020-10-07 03:32 | [7 empty] | 1: 95509 - Planned; 2: 95510 - Planned | #done | FALSE | FALSE | TRUE | FALSE
89712 | WBS.2.1.9.25.1.1 | N | N | Planned | Replicate SPECS and ZUNB materials from MDG to S4 using t-code BD10 | 3 | 2020-10-07 11:45 | 2020-10-07 14:45 | 2020-10-07 | PHANI GHANTASALA | DATA | 10372,90891,92582,92830 | Yet to receive |  |  | PHANI GHANTASALA | 2020-10-07 21:15 | [7 empty] | 1: 10372 - Planned; 2: 90891 - Planned; 3: 92582 - Planned; 4: 92830 - Planned | #done | FALSE | FALSE | FALSE | FALSE
10503 | WBS.2.1.9.16.1.1 | N | N | Planned | Generate Replication Validation reports - AS8 Procured materials (Basic, Plant, Storage Location, Sales views) | 2 | 2020-10-08 07:45 | 2020-10-08 09:45 | 2020-10-08 | ANKIT AGARWAL | DATA | 5121 | #done |  |  | Ishaq | 2020-10-08 17:15 | [7 empty] | 1: 5121 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5429 | WBS.2.2.1.7.13.9 | N | N | Planned | ITR_C0055 - Execute Load program - Convert Measuring Points (with catalogs) – Maintelligence | 2 | 2020-10-06 12:30 | 2020-10-06 14:30 | 2020-10-06 | PHANI GHANTASALA | Data | 5428 | #done |  |  | PHANI GHANTASALA | 2020-10-06 22:00 | [7 empty] | 1: 5428 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82854 | WBS.2.1.8.1.1.54 | N | N | Planned | PTM_C0082 - Execute Load in S/4 - upload routings for Repetitive Manufacturing | 1 | 2020-10-08 07:00 | 2020-10-08 08:00 | 2020-10-08 | ANURAG ANAND | DATA | 82855,92189 | #done |  |  | ANURAG ANAND | 2020-10-08 16:30 | Material | [6 empty] | 1: 82855 - Planned; 2: 92189 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10528 | WBS.2.1.8.1.1.20 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - Procured materials - Classification View | 1 | 2020-10-07 13:45 | 2020-10-07 14:45 | 2020-10-07 | ANJALI SINHA | DATA | 5100 | #start |  |  | Krishna | 2020-10-07 23:15 | Material | [6 empty] | 1: 5100 - Planned | #done | TRUE | FALSE | FALSE | FALSE
89970 | WBS.2.1.8.1.1.69 | N | N | Planned | RTR_C0246 - Execute Load Program - Apportionment Structure For Co-Products | 1 | 2020-10-08 06:20 | 2020-10-08 07:20 | 2020-10-08 | PHANI GHANTASALA | DATA | 89971 | #done |  |  | PHANI GHANTASALA | 2020-10-08 15:50 | Material | [6 empty] | 1: 89971 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5121 | WBS.2.1.9.19.1.1 | N | N | Planned | Replicate Asset Suite Procured Materials from MDG to S/4HANA using t-code BD10 | 9 | 2020-10-07 14:45 | 2020-10-08 07:45 | 2020-10-08 | PHANI GHANTASALA | DATA | 10307,10414,10413,10424,10430,68525,92582,92830 | #done |  |  | PHANI GHANTASALA | 2020-10-08 00:15 | [7 empty] | 10307 - Planned | 10414 - Planned | 10413 - Planned | 10424 - Planned | 10430 - Planned | 68525 - Planned | 92582 - Planned | 92830 - Planned |  |  |  |  | #done | FALSE | FALSE | TRUE | FALSE
5193 | WBS.2.1.8.1.1.51 | N | N | Planned | PTM_C0082 - Execute Actual Load - Convert Routings | 4 | 2020-10-08 07:00 | 2020-10-08 11:00 | 2020-10-08 | ANURAG ANAND | DATA | 10024 | #done |  |  | ANURAG ANAND | 2020-10-08 16:30 | Material | [6 empty] | 1: 10024 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92867 | WBS.2.1.9.31.1.1 | N | N | Planned | Execute Preload ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 1 | 2020-10-08 11:15 | 2020-10-08 12:15 | 2020-10-08 | ANKIT AGARWAL | DATA | 92777,92809,10428 | #done |  |  | ANKIT AGARWAL | 2020-10-08 20:45 | [6 empty] | 1 | 1: 92777 - Planned; 2: 92809 - Planned; 3: 10428 - Planned | #done | FALSE | FALSE | TRUE | FALSE
80859 | WBS.2.1.9.17.1.1 | N | N | Planned | Replicate AS8 Procured Materials Classifiation View from MDG to S/4HANA using change pointers | 14 | 2020-10-08 11:15 | 2020-10-09 09:15 | 2020-10-09 | PHANI GHANTASALA | DATA | 10429,10428 | #done |  |  | PHANI GHANTASALA | 2020-10-08 20:45 | [7 empty] | 1: 10429 - Planned; 2: 10428 - Planned | #done | FALSE | FALSE | TRUE | FALSE
89711 | WBS.2.1.8.1.1.28 | N | N | Planned | Generate Replication Validation reports - SPECS and ZUNB materials | 2 | 2020-10-07 14:45 | 2020-10-07 16:45 | 2020-10-07 | ANKIT AGARWAL | DATA | 89712 | #start |  |  | Ishaq | 2020-10-08 00:15 | Material | [6 empty] | 1: 89712 - Planned | #done | TRUE | FALSE | FALSE | FALSE
5395 | WBS.2.1.9.21.1.4 | N | N | Planned | ITR_C0018 - Execute Preload - Convert equipment – AS8 | 4 | 2020-10-08 11:15 | 2020-10-08 15:15 | 2020-10-08 | VENKATESH GANESHAN | DATA | 5393,82989,10428 | #done |  |  | VENKATESH GANESHAN | 2020-10-08 20:45 | [6 empty] | 1 | 1: 5393 - Planned; 2: 82989 - Complete; 3: 10428 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5415 | WBS.2.2.1.7.13.7 | N | N | Planned | IT ITR_C0020 - Execute Transform Program - Convert BOM – Functional Location Conversion – AS8 | 4 | 2020-10-08 11:15 | 2020-10-08 15:15 | 2020-10-08 | DEEPA SAW | Data | 5393,5408,10428 | #done |  |  | DEEPA SAW | 2020-10-08 20:45 | [7 empty] | 1: 5393 - Planned; 2: 5408 - Planned; 3: 10428 - Planned | #done | FALSE | FALSE | TRUE | FALSE
9804 | WBS.2.2.1.7.13.21 | N | N | Planned | PTM_C0082 - Execute Preload - upload routes for Repetitive Manufacturing (Simulation Mode) | 3 | 2020-10-08 01:00 | 2020-10-08 04:00 | 2020-10-08 | ANURAG ANAND | Data | 9803,10120,89709 | #done |  |  | ANURAG ANAND | 2020-10-08 10:30 | [7 empty] | 1: 9803 - Planned; 2: 10120 - Planned; 3: 89709 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5468 | WBS.2.2.1.7.13.6 | N | N | Planned | ITR_C0038.6 - Execute Transform program - Convert Task Lists - General Conversion – AS8 | 2 | 2020-10-08 11:15 | 2020-10-08 13:15 | 2020-10-08 | JASPREET SINGH | Data | 5408,10428 | #done |  |  | Soham Saha | 2020-10-08 20:45 | [7 empty] | 1: 5408 - Planned; 2: 10428 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5248 | WBS.2.2.1.7.13.35 | N | N | Planned | PTP_C0008.1 - Execute Transform program - Convert Purchase Info Record - AS8 | 3 | 2020-10-08 11:15 | 2020-10-08 14:15 | 2020-10-08 | JASPREET SINGH | Data | 10428,89675,89679 | #done |  |  | JASPREET SINGH | 2020-10-08 20:45 | [7 empty] | 1: 10428 - Planned; 2: 89675 - Planned; 3: 89679 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
89972 | WBS.2.1.8.2.1.9 | N | N | Planned | RTR_C0246 - Execute Preload - Apportionment Structure For Co-Products | 2 | 2020-10-08 01:00 | 2020-10-08 03:00 | 2020-10-08 | PHANI GHANTASALA | DATA | 89710,89973 | #done |  |  | PHANI GHANTASALA | 2020-10-08 10:30 | Material | [6 empty] | 1: 89710 - Planned; 2: 89973 - Planned | #done | FALSE | FALSE | TRUE | FALSE
89766 | WBS.2.2.1.7.16.5 | N | N | Planned | Provide MARA and MARC extracts after materials sign-off to help prepare file for Procurement MDM | 1 | 2020-10-08 11:15 | 2020-10-08 12:15 | 2020-10-08 | PRADEEP CHEEDALLA | DATA | 10428 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-08 20:45 | [7 empty] | 1: 10428 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10472 | WBS.2.1.15.28.1.1 | N | N | Planned | ITR_C0055 - Execute Transform program - Measuring Points Classification | 2 | 2020-10-06 14:30 | 2020-10-06 16:30 | 2020-10-06 | JASPREET SINGH | DATA | 5429,82569 | #done |  |  | Soham Saha | 2020-10-07 | [6 empty] | 1 | 1: 5429 - Planned; 2: 82569 - In-Progress | #done | FALSE | FALSE | TRUE | FALSE
5453 | WBS.2.1.8.2.1.13 | N | N | Planned | ITR_C0038.2 - Execute Transform program - Convert Task Lists – Functional Location Conversion - Maintelligence | 4 | 2020-10-06 16:30 | 2020-10-07 04:30 | 2020-10-07 | ANKIT AGARWAL | Data | 5393,3967,82569,82900 | #done |  |  | Soham Saha | 2020-10-07 02:00 | [6 empty] | 1 | 1: 5393 - Planned; 2: 3967 - Complete; 3: 82569 - In-Progress; 4: 82900 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10473 | WBS.2.1.15.28.1.3 | N | N | Planned | ITR_C0055 - Execute Load - Measuring Points Classification | 1 | 2020-10-06 16:30 | 2020-10-07 01:30 | 2020-10-07 | PHANI GHANTASALA | DATA | 10472 | #done |  |  | PHANI GHANTASALA | 2020-10-07 02:00 | [7 empty] | 1: 10472 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5186 | WBS.2.2.1.7.16.5 | N | N | Planned | Replicate MBOMs (including Repetitive MFG BOMs from RTR) from MDG to S/4HANA | 4 | 2020-10-09 01:00 | 2020-10-09 05:00 | 2020-10-09 | PHANI GHANTASALA | DATA | 10334,9801 | #done |  |  | PHANI GHANTASALA | 2020-10-09 10:30 | [7 empty] | 1: 10334 - Planned; 2: 9801 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92869 | WBS.2.1.15.16.1.4 | N | N | Planned | Execute Load ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 1 | 2020-10-08 14:15 | 2020-10-08 15:15 | 2020-10-08 | DEBRAJ PAL | DATA | 92868 | #done |  |  | DEBRAJ PAL | 2020-10-08 23:45 | [7 empty] | 1: 92868 - Planned | #done | FALSE | FALSE | TRUE | FALSE
68443 | WBS.2.1.15.16.1.3 | N | N | Planned | ITR_C0055 - Execute Transform program - Measuring Points-Entry List | 1 | 2020-10-07 01:30 | 2020-10-07 02:30 | 2020-10-07 | JASPREET SINGH | DATA | 5382,5388,5393,10473 | Yet to receive |  |  | Soham Saha | 2020-10-07 11:00 | [6 empty] | 1 | 1: 5382 - Planned; 2: 5388 - Planned; 3: 5393 - Planned; 4: 10473 - Planned | #done | FALSE | FALSE | FALSE | FALSE
68444 | WBS.2.1.15.16.1.7 | N | N | Planned | ITR_C0055 - Execute Load - Measuring Points-Entry List | 1 | 2020-10-07 02:30 | 2020-10-07 03:30 | 2020-10-07 | PHANI GHANTASALA | DATA | 68443 | #done |  |  | PHANI GHANTASALA | 2020-10-07 12:00 | [6 empty] | 1 | 1: 68443 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5397 | WBS.2.1.9.18.1.3 | N | N | Planned | ITR_C0018 - Execute Load program - Convert equipment – AS8 | 5 | 2020-10-08 16:15 | 2020-10-09 05:15 | 2020-10-09 | VENKATESH GANESHAN | DATA | 5396 | #done |  |  | VENKATESH GANESHAN | 2020-10-09 01:45 | [7 empty] | 1: 5396 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5448 | WBS.2.1.9.19.1.5 | N | N | Planned | ITR_C0038.1 - Execute Transform program - Convert Task Lists – Functional Location – AS8 | 2 | 2020-10-08 11:15 | 2020-10-08 13:15 | 2020-10-08 | ANKIT AGARWAL | DATA | 5393,5408,10428,5456,82900 | #done |  |  | ANKIT AGARWAL | 2020-10-08 20:45 | [7 empty] | 1: 5393 - Planned; 2: 5408 - Planned; 3: 10428 - Planned; 4: 5456 - Planned; 5: 82900 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92874 | WBS.2.1.15.19.1.3 | N | N | Planned | Execute Preload ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 1 | 2020-10-09 01:00 | 2020-10-09 02:00 | 2020-10-09 | ANKIT AGARWAL | DATA | 92870 | #done |  |  | Ishaq | 2020-10-09 10:30 | [6 empty] | 1 | 1: 92870 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90049 | WBS.2.1.8.1.1.30 | N | N | Planned | Change BOM partner profile to pass immediately in MDG | 0.25 | 2020-10-09 06:30 | 2020-10-09 06:45 | 2020-10-09 | PHANI GHANTASALA | DATA | 9801,10334,9802 | #done |  |  | PHANI GHANTASALA | 2020-10-09 16:00 | Material | [6 empty] | 1: 9801 - Planned; 2: 10334 - Planned; 3: 9802 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10114 | WBS.2.2.1.7.13.17 | N | N | Planned | PTM_C0085 - Execute Preload Transform - Convert Production Versions for Repetitive Manufacturing | 2 | 2020-10-09 06:30 | 2020-10-09 08:30 | 2020-10-09 | PRADEEP CHEEDALLA | Data | 9809,9807,9802 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-09 16:00 | [7 empty] | 1: 9809 - Planned; 2: 9807 - Planned; 3: 9802 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10023 | WBS.2.1.9.8.1.7 | N | N | Planned | PTM_C0082 - Execute Preload for Convert Routing (simulation mode) | 2 | 2020-10-08 01:00 | 2020-10-08 03:00 | 2020-10-08 | ANURAG ANAND | DATA | 89709,80758 | #done |  |  | ANURAG ANAND | 2020-10-08 10:30 | [7 empty] | 1: 89709 - Planned; 2: 80758 - Planned | #done | FALSE | FALSE | TRUE | FALSE
95613 |  | N | N |  | Run routing component allocation logic after BOM replication to S4 | 2 | 2020-10-09 08:00 | 2020-10-09 10:00 | 2020-10-09 | ANURAG ANAND | DATA | 5187,5193 | #done |  |  | ANURAG ANAND | 2020-10-09 17:30 | [7 empty] | 1: 5187 - Planned; 2: 5193 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5455 | WBS.2.1.8.2.1.24 | N | N | Planned | ITR_C0038.2 - Execute Load program - Convert Task Lists – Functional Location Conversion - Maintelligence | 1 | 2020-10-07 08:00 | 2020-10-07 09:00 | 2020-10-07 | DEBRAJ PAL | DATA | 5454 | #done |  |  | DEBRAJ PAL | 2020-10-07 17:30 | Material | [5 empty] | 1 | 1: 5454 - Planned | #done | FALSE | FALSE | TRUE | FALSE
94770 | WBS.2.1.9.19.1.7 | N | N | Planned | Replicate changes for Unit of Issue and Printed boards master data updates needed for BOMs | 1 | 2020-10-07 01:00 | 2020-10-07 02:00 | 2020-10-07 | PHANI GHANTASALA | DATA | 94769 | #done |  |  | PHANI GHANTASALA | 2020-10-07 10:30 | [7 empty] | 1: 94769 - Planned | #done | FALSE | TRUE | TRUE | FALSE
82908 | WBS.2.1.15.8.1.2 | N | N | Planned | ITR_C0175 - Execute Transform program - Convert Documents for measuring points | 1 | 2020-10-07 10:00 | 2020-10-07 11:00 | 2020-10-07 | JASPREET SINGH | DATA | 5430 | #done |  |  | Soham Saha | 2020-10-07 19:30 | [7 empty] | 1: 5430 - Planned | #done | FALSE | FALSE | TRUE | FALSE
9798 | WBS.2.1.9.18.1.1 | N | N | Planned | PTM_C0080 - Execute Transform - Upload for Repetitive Manufacturing | 5 | 2020-10-07 11:00 | 2020-10-07 16:00 | 2020-10-07 | PRADEEP CHEEDALLA | DATA | 9797,10372,94770 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-07 20:30 | [7 empty] | 1: 9797 - Planned; 2: 10372 - Planned; 3: 94770 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10110 | WBS.2.1.8.1.1.47 | N | N | Planned | PTM_C0080 - Execute Transform - Convert Bill of Materials (MBOMS) | 8 | 2020-10-07 11:00 | 2020-10-08 03:00 | 2020-10-08 | PRADEEP CHEEDALLA | DATA | 10372,80758,94770,94724 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-07 20:30 | Material | [6 empty] | 1: 10372 - Planned; 2: 80758 - Planned; 3: 94770 - Planned; 4: 94724 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92876 | WBS.2.1.9.31.1.3 | N | N | Planned | Execute Load ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 1 | 2020-10-09 08:00 | 2020-10-09 09:00 | 2020-10-09 | VENKATESH GANESHAN | DATA | 92875 | #done |  |  | VENKATESH GANESHAN | 2020-10-09 17:30 | [6 empty] | 1 | 1: 92875 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10022 | WBS.2.1.9.28.1.1 | N | N | Planned | PTM_C0085 - Execute Preload Transform - Convert Production Versions | 2 | 2020-10-09 08:00 | 2020-10-09 10:00 | 2020-10-09 | PRADEEP CHEEDALLA | DATA | 5195,10334,5187,80758 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-09 17:30 | [7 empty] | 1: 5195 - Planned; 2: 10334 - Planned; 3: 5187 - Planned; 4: 80758 - Planned | #done | FALSE | FALSE | TRUE | FALSE
9810 | WBS.2.1.15.30.1.1 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Production Versions for Repetitive Manufacturing | 2 | 2020-10-09 08:45 | 2020-10-09 10:45 | 2020-10-09 | PHANI GHANTASALA | DATA | 10115 | #done |  |  | PHANI GHANTASALA | 2020-10-09 18:15 | [7 empty] | 1: 10115 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10112 | WBS.2.1.8.2.1.18 | N | N | Planned | ITR_C0028 - Execute Transform program - Convert Equipment Classification values - AS8 | 2 | 2020-10-09 07:00 | 2020-10-09 09:00 | 2020-10-09 | ANJALI SINHA | DATA | 5385,5398 | #done |  |  | ANJALI SINHA | 2020-10-09 16:30 | Material | [6 empty] | 1: 5385 - Planned; 2: 5398 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
80860 | WBS.2.1.15.11.1.3 | N | N | Planned | Generate Replication Validation reports - AS8 Procured Materials Classification view | 2 | 2020-10-09 09:15 | 2020-10-09 11:15 | 2020-10-09 | ANKIT AGARWAL | DATA | 80859 | #done |  |  | Ishaq | 2020-10-09 18:45 | [7 empty] | 1: 80859 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5201 | WBS.2.1.9.29.1.1 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Production versions | 1.5 | 2020-10-09 12:00 | 2020-10-09 13:30 | 2020-10-09 | PHANI GHANTASALA | DATA | 10021 | Yet to receive |  |  | PHANI GHANTASALA | 2020-10-09 21:30 | [6 empty] | 1 | 1: 10021 - Planned | #done | FALSE | FALSE | FALSE | FALSE
5250 | WBS.2.1.8.1.1.76 | N | N | Planned | PTP_C0008.1 - Execute Load program - Convert Purchase Info Record - AS8 | 13 | 2020-10-08 16:15 | 2020-10-09 13:15 | 2020-10-09 | JASPREET SINGH | DATA | 5249 | #issue |  |  | JASPREET SINGH | 2020-10-09 01:45 | Material | [6 empty] | 1: 5249 - Planned | #done | FALSE | TRUE | FALSE | FALSE
5478 | WBS.2.2.1.7.13.8 | N | N | Planned | ITR_C0050.1 - Execute Transform program - Convert Maintenance Plans Conversion - Maintelligence | 2 | 2020-10-07 11:45 | 2020-10-07 13:45 | 2020-10-07 | ANKIT AGARWAL | Data | 9400,5430 | #done |  |  | Ishaq | 2020-10-07 21:15 | [7 empty] | 1: 9400 - Planned; 2: 5430 - Planned | #done | FALSE | FALSE | TRUE | FALSE
10032 | WBS.2.2.1.7.13.34 | N | N | Planned | PTM_C0205 - Execute Transform Program - Convert Product Master | 5 | 2020-10-09 11:00 | 2020-10-09 16:00 | 2020-10-09 | DEEPA SAW | Data | 10428,3956,8861,8862,94304,94302,94307,94305,96567,96568,96699,96700 | #done |  |  | Krishna | 2020-10-09 20:30 | [7 empty] | 10428 - Planned | 3956 - Planned | 8861 - Planned | 8862 - Planned | 94304 - Planned | 94302 - Planned | 94307 - Planned | 94305 - Planned | 96567 - Planned | 96568 - Planned | 96699 - Planned | 96700 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5437 | WBS.2.1.15.7.1.4 | N | N | Planned | ITR_C0028 - Execute Load program - Convert Equipment Classification Values – AS8 | 1 | 2020-10-09 09:20 | 2020-10-09 10:20 | 2020-10-09 | VENKATESH GANESHAN | DATA | 10113 | #done |  |  | VENKATESH GANESHAN | 2020-10-09 18:50 | [6 empty] | 1 | 1: 10113 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
9800 | WBS.2.1.8.1.1.48 | N | N | Planned | PTM_C0080 - Execute Load in MDG - upload for Repetitive Manufacturing | 3 | 2020-10-08 07:30 | 2020-10-08 10:30 | 2020-10-08 | PRADEEP CHEEDALLA | DATA | 90050,9799,90084 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-08 17:00 | Material | [6 empty] | 1: 90050 - Planned; 2: 9799 - Planned; 3: 90084 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5183 | WBS.2.1.9.4.1.10 | N | N | Planned | PTM_C0080 - Execute Load in MDG - Convert Bill of Materials (MBOMS) | 8 | 2020-10-08 07:30 | 2020-10-08 15:30 | 2020-10-08 | PRADEEP CHEEDALLA | DATA | 90050,10111,90084,94724 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-08 17:00 | Material | [6 empty] | 1: 90050 - Planned; 2: 10111 - Planned; 3: 90084 - Planned; 4: 94724 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5450 | WBS.2.1.8.1.1.17 | N | N | Planned | ITR_C0038.1 - Execute Load program - Convert Task Lists – Functional Location – AS8 | 5 | 2020-10-08 14:15 | 2020-10-09 03:15 | 2020-10-09 | DEBRAJ PAL | DATA | 5449 | #done |  |  | DEBRAJ PAL | 2020-10-08 23:45 | Material | [6 empty] | 1: 5449 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5215 | WBS.2.1.8.2.1.23 | N | N | Planned | PTM_C0092 - Execute Load Program - Convert Product Cost Collectors - PE | 1 | 2020-10-12 11:00 | 2020-10-12 12:00 | 2020-10-12 | PHANI GHANTASALA | DATA | 4056,11032 | #done |  |  | PHANI GHANTASALA | 2020-10-12 20:30 | Material | [6 empty] | 1: 4056 - Planned; 2: 11032 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5480 | WBS.2.1.15.24.1.3 | N | N | Planned | ITR_C0050.1 - Execute Load program - Convert Maintenance Plans Conversion - Maintelligence | 2 | 2020-10-07 15:15 | 2020-10-08 01:15 | 2020-10-08 | VENKATESH GANESHAN | DATA | 5479 | #done |  |  | VENKATESH GANESHAN | 2020-10-08 00:45 | [6 empty] | 1 | 1: 5479 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90959 | WBS.2.1.9.28.1.3 | N | N | Planned | Identify changes in material master in MDG not made by conversion | 3 | 2020-10-09 13:30 | 2020-10-09 16:30 | 2020-10-09 | SHANKAR RAMNARAYANAN | DATA | 90052 | #done |  |  | SHANKAR RAMNARAYANAN | 2020-10-09 23:00 | [7 empty] | 1: 90052 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
82906 | WBS.2.1.9.26.1.6 | N | N | Planned | ITR_C0175 - Execute Load program - Convert Documents for measuring points | 1 | 2020-10-07 15:30 | 2020-10-07 16:30 | 2020-10-07 | VENKATESH GANESHAN | DATA | 82907 | #start |  |  | VENKATESH GANESHAN | 2020-10-08 01:00 | [7 empty] | 1: 82907 - Planned | #done | TRUE | FALSE | FALSE | FALSE
5470 | WBS.2.1.8.1.1.29 | N | N | Planned | ITR_C0038.6 - Execute Load program - Convert Task Lists - General Conversion – AS8 | 1 | 2020-10-08 15:00 | 2020-10-08 16:00 | 2020-10-08 | DEBRAJ PAL | DATA | 5469 | #done |  |  | DEBRAJ PAL | 2020-10-09 00:30 | Material | [6 empty] | 1: 5469 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5245 | WBS.2.1.8.1.1.57 | N | N | Planned | PTP_C0008 - Execute Load program - Convert Purchase Info Record - ECC | 4 | 2020-10-09 15:15 | 2020-10-12 03:15 | 2020-10-12 | ANJALI SINHA | DATA | 5244,5251,95364 | #done |  |  | ANJALI SINHA | 2020-10-10 00:45 | Material | [6 empty] | 1: 5244 - Planned; 2: 5251 - Planned; 3: 95364 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90960 | WBS.2.1.9.28.1.3 | N | N | Planned | Replicate changes in material master not made by conversion from MDG to S4 | 2 | 2020-10-09 16:30 | 2020-10-12 02:30 | 2020-10-12 | SHANKAR RAMNARAYANAN | DATA | 90959 | #done |  |  | SHANKAR RAMNARAYANAN | 2020-10-10 02:00 | [7 empty] | 1: 90959 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5253 | WBS.2.1.8.1.1.77 | N | N | Planned | PTP_C0200 - Execute Transform Program - Source List Conversion - AS8 | 2 | 2020-10-09 15:15 | 2020-10-12 01:15 | 2020-10-12 | ANJALI SINHA | DATA | 5251,10428 | #done |  |  | Krishna | 2020-10-10 00:45 | Material | [6 empty] | 1: 5251 - Planned; 2: 10428 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5229 | WBS.2.1.8.1.1.71 | N | N | Planned | PTM_C0205 - Execute Load Program - Convert Product Master | 10 | 2020-10-12 01:00 | 2020-10-12 11:00 | 2020-10-12 | DEEPA SAW | DATA | 10033,94318,94316,94315,94314,94312,94311,96569,96570,96701,96702 | #done |  |  | Krishna | 2020-10-12 10:30 | Material | [6 empty] | 10033 - Planned | 94318 - Planned | 94316 - Planned | 94315 - Planned | 94314 - Planned | 94312 - Planned | 94311 - Planned | 96569 - Planned | 96570 - Planned | 96701 - Planned | 96702 - Planned |  | #done | FALSE | FALSE | TRUE | FALSE
90052 | WBS.2.1.9.8.1.3 | N | N | Planned | Turn ON DRFOUT, Turn OFF Change Pointers for CLFMAS, MATMAS, MATQM in MDG | 0.25 | 2020-10-09 13:15 | 2020-10-09 13:30 | 2020-10-09 | PHANI GHANTASALA | DATA | 10428,89709,10427,90079 | #done |  |  | PHANI GHANTASALA | 2020-10-09 22:45 | [7 empty] | 1: 10428 - Planned; 2: 89709 - Planned; 3: 10427 - Planned; 4: 90079 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5473 | WBS.2.1.9.8.1.5 | N | N | Planned | ITR_C0050 - Execute Transform Program - Convert Maintenance Plans Conversion – AS8 | 3 | 2020-10-09 14:00 | 2020-10-09 17:00 | 2020-10-09 | JASPREET SINGH | DATA | 5451,5471 | #done |  |  | Soham Saha | 2020-10-09 23:30 | [7 empty] | 1: 5451 - Planned; 2: 5471 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5258 | WBS.2.1.8.1.1.64 | N | N | Planned | PTP_C0200.1 - Execute Transform Program - Convert Source List - ECC | 2 | 2020-10-12 05:15 | 2020-10-12 07:15 | 2020-10-12 | JASPREET SINGH | DATA | 5236,5246 | #done |  |  | JASPREET SINGH | 2020-10-12 14:45 | Material | [6 empty] | 1: 5236 - Planned; 2: 5246 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5255 | WBS.2.1.8.1.1.65 | N | N | Planned | PTP_C0200 - Execute Load Program - Source List Conversion - AS8 | 3 | 2020-10-12 07:00 | 2020-10-12 10:00 | 2020-10-12 | ANJALI SINHA | DATA | 5254 | #done |  |  | Krishna | 2020-10-12 16:30 | Material | [6 empty] | 1: 5254 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5417 | WBS.2.1.9.30.1.1 | N | N | Planned | ITR_C0020 - Execute Load Program - Convert BOM – Functional Location Conversion – AS8 | 4 | 2020-10-09 15:00 | 2020-10-12 03:00 | 2020-10-12 | PHANI GHANTASALA | DATA | 5416 | #done |  |  | PHANI GHANTASALA | 2020-10-10 00:30 | [7 empty] | 1: 5416 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5475 | WBS.2.1.9.19.1.6 | N | N | Planned | ITR_C0050 - Execute Load Program - Convert Maintenance Plans Conversion – AS8 | 2 | 2020-10-12 01:00 | 2020-10-12 03:00 | 2020-10-12 | VENKATESH GANESHAN | DATA | 5474,95484 | #done |  |  | VENKATESH GANESHAN | 2020-10-12 10:30 | [7 empty] | 1: 5474 - Planned; 2: 95484 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5260 | WBS.2.1.15.23.1.3 | N | N | Planned | PTP_C0200.1 - Execute Load Program - Convert Source List - ECC | 2 | 2020-10-12 08:15 | 2020-10-12 10:15 | 2020-10-12 | JASPREET SINGH | DATA | 5259 | #done |  |  | JASPREET SINGH | 2020-10-12 17:45 | [6 empty] | 1 | 1: 5259 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5400 | WBS.2.1.9.4.1.8 | N | N | Planned | ITR_C0024 - Execute Transform Program - Convert BOM - Material / Assemblies Conversion – AS8 | 2 | 2020-10-12 08:30 | 2020-10-12 10:30 | 2020-10-12 | PRADEEP CHEEDALLA | DATA | 5408,10428,5418 | #done |  |  | Aarthi | 2020-10-12 18:00 | Material | [6 empty] | 1: 5408 - Planned; 2: 10428 - Planned; 3: 5418 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5402 | WBS.2.1.15.17.1.8 | N | N | Planned | ITR_C0024 - Execute Load Program - Convert BOM - Material / Assemblies Conversion – AS8 | 5 | 2020-10-12 11:30 | 2020-10-12 16:30 | 2020-10-12 | PRADEEP CHEEDALLA | DATA | 5401 | #done |  |  | Aarthi | 2020-10-12 21:00 | Material | [6 empty] | 1: 5401 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92815 | WBS.2.1.8.2.1.17 | N | N | Planned | Execute Load ITR_C0247 - NRX 3D Enterprise Document Conversion | 8 | 2020-10-12 20:00 | 2020-10-13 12:00 | 2020-10-13 | DEBRAJ PAL | DATA | 92814 | #done |  |  | DEBRAJ PAL | 2020-10-13 05:30 | Material | [6 empty] | 1: 92814 - Planned | #done | FALSE | FALSE | TRUE | FALSE
4971 | WBS.2.1.8.1.1.70 | N | N | Planned | DAT_C0234 - Execute Transform Program -Conversion of Contractors & non-CPG employees - Eng. Contractors | 2 | 2020-10-09 12:15 | 2020-10-09 14:15 | 2020-10-09 | ANJALI SINHA | DATA | 9101,93067,91838 | #done |  |  | ANJALI SINHA | 2020-10-09 21:45 | Material | [6 empty] | 1: 9101 - Planned; 2: 93067 - Complete; 3: 91838 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
4973 | WBS.2.1.8.2.1.10 | N | N | Planned | DAT_C0234 - Execute Load Program - Conversion of Contractors & non-CPG employees - Eng. Contractors | 2 | 2020-10-09 14:30 | 2020-10-09 16:30 | 2020-10-09 | ANURAG ANAND | DATA | 4972 | #done |  |  | ANURAG ANAND | 2020-10-10 | Material | [6 empty] | 1: 4972 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92813 | WBS.2.1.15.20.1.3 | N | N | Planned | Execute Preload ITR_C0247 - NRX 3D Enterprise Document Conversion | 4 | 2020-10-12 13:00 | 2020-10-12 17:00 | 2020-10-12 | ANJALI SINHA | DATA | 92777,5393,5398,92788,10428,95626 | #done |  |  | ANJALI SINHA | 2020-10-12 22:30 | [6 empty] | 1 | 1: 92777 - Planned; 2: 5393 - Planned; 3: 5398 - Planned; 4: 92788 - Planned; 5: 10428 - Planned; 6: 95626 - Planned | #issue | FALSE | FALSE | TRUE | FALSE
10474 | WBS.2.1.15.15.1.2 | N | N | Planned | ITR_C0061 - Execute Preload - Convert Work Center - HR assignments | 1 | 2020-10-12 01:00 | 2020-10-12 02:00 | 2020-10-12 | VENKATESH GANESHAN | DATA | 4974 | #done |  |  | VENKATESH GANESHAN | 2020-10-12 10:30 | [7 empty] | 1: 4974 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82771 | WBS.2.1.8.1.1.3 | N | N | Planned | MDG_C0098 - Execute Extracts from AS8 for Delta load of AS8 Procured materials | 6 | 2020-10-12 06:30 | 2020-10-12 12:30 | 2020-10-12 | ANJALI SINHA | DATA | 10428,10854,89967 | #done |  |  | ANJALI SINHA | 2020-10-12 16:00 | Material | [6 empty] | 1: 10428 - Planned; 2: 10854 - Planned; 3: 89967 - Planned | #done | FALSE | FALSE | TRUE | FALSE
89987 | WBS.2.1.8.2.2.8 | N | N | Planned | Execute T-4 Extracts for Asset Suite | 2.5 | 2020-10-12 06:30 | 2020-10-12 09:00 | 2020-10-12 | ANJALI SINHA | DATA | 89967 | #done |  |  | ANJALI SINHA | 2020-10-12 16:00 | Material | [6 empty] | 1: 89967 - Planned | #done | FALSE | FALSE | TRUE | FALSE
94400 | WBS.2.1.8.2.2.3 | N | N | Planned | Execute T-4 Extracts for MP2 | 2.5 | 2020-10-12 07:15 | 2020-10-12 09:45 | 2020-10-12 | ANJALI SINHA | DATA | 94359 | #done |  |  | ANJALI SINHA | 2020-10-12 16:45 | Material | [6 empty] | 1: 94359 - Planned | #done | FALSE | FALSE | TRUE | FALSE
94357 | WBS.2.2.1.7.26.1 | N | N | Planned | Execute Preload ITR_C0067.1 Convert Scheduled Maintenance Plans (T-4 Days) - MP2 | 1 | 2020-10-12 09:45 | 2020-10-12 10:45 | 2020-10-12 | JASPREET SINGH | DATA | 94359,94400,92877 | #done |  |  | JASPREET SINGH | 2020-10-12 19:15 | [7 empty] | 1: 94359 - Planned; 2: 94400 - Planned; 3: 92877 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92846 | WBS.2.2.1.7.28.3 | N | N | Planned | Execute Preload ITR_C0032.1 Convert Open work orders – MP2 | 1 | 2020-10-12 09:45 | 2020-10-12 10:45 | 2020-10-12 | ANJALI SINHA | DATA | 94359,94400,92777,92788,92809 | #done |  |  | ANJALI SINHA | 2020-10-12 19:15 | [7 empty] | 1: 94359 - Planned; 2: 94400 - Planned; 3: 92777 - Planned; 4: 92788 - Planned; 5: 92809 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5760 | WBS.2.1.15.12.1.3 | N | N | Planned | ITR_C0032 - Execute Transform program - Convert Open work orders – Asset Suite | 2 | 2020-10-12 10:15 | 2020-10-12 12:15 | 2020-10-12 | ANJALI SINHA | DATA | 10428,5398,5408,89967,89987,90973,94400 | #done |  |  | ANJALI SINHA | 2020-10-12 19:45 | [6 empty] | 1 | 1: 10428 - Planned; 2: 5398 - Planned; 3: 5408 - Planned; 4: 89967 - Planned; 5: 89987 - Planned; 6: 90973 - Planned; 7: 94400 - Planned | #done | FALSE | FALSE | TRUE | FALSE
89993 | WBS.2.2.1.7.13.14 | N | N | Planned | ITR_C0067 - Execute Transform program - Convert Scheduled Maintenance Plans (T-4 Days) - AS8 | 15 | 2020-10-12 10:15 | 2020-10-12 12:15 | 2020-10-12 | ANKIT AGARWAL | Data | 89987,90973,94400,5476 | #done |  |  | ANKIT AGARWAL | 2020-10-12 19:45 | [7 empty] | 1: 89987 - Planned; 2: 90973 - Planned; 3: 94400 - Planned; 4: 5476 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5378 | WBS.2.1.15.6.1.2 | N | N | Planned | ITR_C0061 - Execute Load program - Convert Work Center - HR assignments | 4 | 2020-10-12 06:20 | 2020-10-12 10:20 | 2020-10-12 | VENKATESH GANESHAN | DATA | 10475 | #done |  |  | VENKATESH GANESHAN | 2020-10-12 15:50 | [6 empty] | 1 | 1: 10475 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82772 | WBS.2.1.8.1.1.33 | N | N | Planned | Execute Transform program for DELTA Asset Suite Procured materials | 4 | 2020-10-12 12:30 | 2020-10-12 16:30 | 2020-10-12 | DEEPA SAW | DATA | 82771 | #done |  |  | DEEPA SAW | 2020-10-12 22:00 | Material | [6 empty] | 1: 82771 - Planned | #done | FALSE | FALSE | TRUE | FALSE
94355 | WBS.2.2.1.7.28.1 | N | N | Planned | Execute Load ITR_C0067.1 Convert Scheduled Maintenance Plans (T-4 Days) - MP2 | 1 | 2020-10-12 12:45 | 2020-10-12 13:45 | 2020-10-12 | JASPREET SINGH | DATA | 94356 | #done |  |  | JASPREET SINGH | 2020-10-12 22:15 | [7 empty] | 1: 94356 - Planned | #done | FALSE | FALSE | TRUE | FALSE
5762 | WBS.2.1.15.26.1.1 | N | N | Planned | ITR_C0032 - Execute Load program - Convert Open work orders – Asset Suite | 4 | 2020-10-12 13:15 | 2020-10-13 01:15 | 2020-10-13 | ANJALI SINHA | DATA | 5761 | #done |  |  | ANJALI SINHA | 2020-10-12 22:45 | [6 empty] | 1 | 1: 5761 - Planned | #done | FALSE | FALSE | TRUE | FALSE
89994 | WBS.2.1.15.15.1.6 | N | N | Planned | ITR_C0067 - Execute Load program - Convert Scheduled Maintenance Plans (T-4 Days) - AS8 | 2 | 2020-10-12 13:35 | 2020-10-12 15:35 | 2020-10-12 | ANKIT AGARWAL | DATA | 89996 | #done |  |  | ANKIT AGARWAL | 2020-10-12 23:05 | [7 empty] | 1: 89996 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82773 | WBS.2.1.9.25.1.3 | N | N | Planned | Generate Preload validation reports - DELTA AS8 Procured materials - All Views | 4 | 2020-10-12 16:30 | 2020-10-13 04:30 | 2020-10-13 | DEEPA SAW | DATA | 82772 | #done |  |  | DEEPA SAW | 2020-10-13 02:00 | [7 empty] | 1: 82772 - Planned | #done | FALSE | FALSE | TRUE | FALSE
92844 | WBS.2.2.1.7.26.5 | N | N | Planned | Execute Load ITR_C0032.1 Convert Open work orders – MP2 | 1 | 2020-10-13 01:15 | 2020-10-13 02:15 | 2020-10-13 | ANJALI SINHA | DATA | 92845,5762 | #done |  |  | ANJALI SINHA | 2020-10-13 10:45 | [7 empty] | 1: 92845 - Planned; 2: 5762 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82777 | WBS.2.1.15.15.1.1 | N | N | Planned | Turn OFF DRFOUT, Turn ON Change pointers for CLFMAS, MATMAS, MATQM in MDG for DELTA Procured Materials load | 0.5 | 2020-10-13 11:00 | 2020-10-13 11:30 | 2020-10-13 | PHANI GHANTASALA | DATA | 92471 | #done |  |  | PHANI GHANTASALA | 2020-10-13 20:30 | [7 empty] | 1: 92471 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82778 | WBS.2.1.9.6.1.5 | N | N | Planned | Execute Load in MDG - DELTA AS8 Procured Materials - All Views | 4 | 2020-10-13 11:30 | 2020-10-13 15:30 | 2020-10-13 | DEBRAJ PAL | DATA | 82774,82775,82776,82777,92124,92628 | #done |  |  | DEBRAJ PAL | 2020-10-13 21:00 | [7 empty] | 1: 82774 - Planned; 2: 82775 - Planned; 3: 82776 - Planned; 4: 82777 - Planned; 5: 92124 - Planned; 6: 92628 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90681 | WBS.2.1.9.17.1.3 | N | N | Planned | MDG_C0098 - Execute Transform for DELTA AS8 Materials - Classifications View and generate validation report | 2 | 2020-10-13 15:30 | 2020-10-14 01:30 | 2020-10-14 | ANJALI SINHA | DATA | 82778 | #done |  |  | Krishna | 2020-10-14 01:00 | [7 empty] | 1: 82778 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82779 | WBS.2.1.9.21.1.2 | N | N | Planned | Generate Post Load Validation report - DELTA AS8 Procured materials - All Views | 3 | 2020-10-13 15:30 | 2020-10-14 02:30 | 2020-10-14 | ANJALI SINHA | DATA | 82778 | #done |  |  | Aarthi | 2020-10-14 01:00 | [6 empty] | 1 | 1: 82778 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90679 | WBS.2.1.8.1.1.7 | N | N | Planned | MDG_C0098 - Execute Load in MDG - DELTA AS8 Materials - Classification View and generate validation report | 1 | 2020-10-14 07:00 | 2020-10-14 08:00 | 2020-10-14 | ANJALI SINHA | DATA | 90680 | #done |  |  | Krishna | 2020-10-14 16:30 | Material | [6 empty] | 1: 90680 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82798 | WBS.2.1.9.16.1.3 | N | N | Planned | Replicate DELTA AS8 Procured materials from MDG to S/4HANA | 1.5 | 2020-10-14 08:15 | 2020-10-14 09:45 | 2020-10-14 | PHANI GHANTASALA | DATA | 82780,82781,82782,92627 | #done |  |  | PHANI GHANTASALA | 2020-10-14 17:45 | [7 empty] | 1: 82780 - Planned; 2: 82781 - Planned; 3: 82782 - Planned; 4: 92627 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90677 | WBS.2.1.9.19.1.3 | N | N | Planned | Replicate DELTA AS8 Procured material classifications from MDG to S4 and generate report | 2 | 2020-10-14 08:30 | 2020-10-14 10:30 | 2020-10-14 | PHANI GHANTASALA | DATA | 90678,92627 | #done |  |  | PHANI GHANTASALA | 2020-10-14 18:00 | [7 empty] | 1: 90678 - Planned; 2: 92627 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82799 | WBS.2.1.9.15.1.3 | N | N | Planned | Generate Replication validation report for DELTA AS8 Procured materials - All Views | 2 | 2020-10-14 09:45 | 2020-10-14 11:45 | 2020-10-14 | ANKIT AGARWAL | DATA | 82798 | #done |  |  | Ishaq | 2020-10-14 19:15 | [7 empty] | 1: 82798 - Planned | #done | FALSE | FALSE | TRUE | FALSE
90969 | WBS.2.2.1.7.16.5 | N | N | Planned | Provide MARA and MARC extracts after DELTA AS8 material sign-off to prepare file for Procurement MDM | 1 | 2020-10-14 13:45 | 2020-10-14 14:45 | 2020-10-14 | PRADEEP CHEEDALLA | DATA | 82800 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-14 23:15 | [7 empty] | 1: 82800 - Planned | #done | FALSE | FALSE | TRUE | FALSE
82804 | WBS.2.1.9.19.1.4 | N | N | Planned | Turn-ON DRFOUT, Turn OFF Change pointers for CLFMAS, MATMAS, MATQM in MDG after DELTA AS8 material signoff | 0.5 | 2020-10-14 14:45 | 2020-10-14 15:15 | 2020-10-14 | PHANI GHANTASALA | DATA | 92473 | #done |  |  | PHANI GHANTASALA | 2020-10-15 00:15 | [7 empty] | 1: 92473 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
81155 | WBS.2.2.1.7.13.10 | N | N | Planned | Execute Extracts from AS8 for PTP_C0005.1, ITR_C0062 | 7.5 | 2020-10-16 15:15 | 2020-10-16 22:45 | 2020-10-16 | ANJALI SINHA | Data | 5251,3968,82187 | #done |  |  | ANJALI SINHA | 2020-10-17 00:45 | [7 empty] | 1: 5251 - Planned; 2: 3968 - Complete; 3: 82187 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
94412 | WBS.2.1.15.30.1.1 | N | N | Planned | Execute FCW Extracts from MP2 for ITR_C0067.1 and ITR_C0062.1 | 3.5 | 2020-10-16 17:30 | 2020-10-16 21:00 | 2020-10-16 | ANJALI SINHA | DATA | 36505 | #done |  |  | ANJALI SINHA | 2020-10-17 03:00 | [7 empty] | 1: 36505 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
8874 | WBS.2.2.1.7.13.13 | N | N | Planned | PTH - PTM_C0201 - Execute Inventory Extracts From Elixir | 1 | 2020-10-16 17:30 | 2020-10-16 18:30 | 2020-10-16 | ANJALI SINHA | Data | 8864,36505,68450 | #done |  |  | ANJALI SINHA | 2020-10-17 03:00 | [7 empty] | 1: 8864 - Planned; 2: 36505 - Planned; 3: 68450 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
94450 | WBS.2.1.13.1.1.12 | N | N | Planned | SCH - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2020-10-16 17:30 | 2020-10-16 18:30 | 2020-10-16 | ANJALI SINHA | DATA | 5231,36505,68450 | Yet to receive |  |  | ANJALI SINHA | 2020-10-17 03:00 | [7 empty] | 1: 5231 - Planned; 2: 36505 - Planned; 3: 68450 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
29564 | WBS.2.2.1.7.11.1 | N | N | Planned | Extract MAP (Moving Average Price) values from AS8 for Costing/AUP as of Cutoff date | 1 | 2020-10-16 17:30 | 2020-10-16 18:30 | 2020-10-16 | ANJALI SINHA | DATA | 36505 | Yet to receive |  |  | ANJALI SINHA | 2020-10-17 03:00 | [7 empty] | 1: 36505 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
81154 | WBS.2.1.16.4.2.16 | N | N | Planned | Execute Final Cutover Extracts from AS8 - for PTM_C0201, ITR_0035, ITR_C0067 | 3 | 2020-10-16 17:30 | 2020-10-16 20:30 | 2020-10-16 | ANJALI SINHA | DATA | 3968,36505 | Yet to receive |  |  | ANJALI SINHA | 2020-10-17 03:00 | [7 empty] | 1: 3968 - Complete; 2: 36505 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
81153 | WBS.2.2.1.7.20.1 | N | N | Planned | Execute Final Cutover Extracts from ECC - Large (Sales Orders, Pricing Records, Pricing Agrmts., Inventory) | 3.5 | 2020-10-16 18:00 | 2020-10-16 21:30 | 2020-10-16 | ANJALI SINHA | DATA | 3964,36505,95439 | #done |  |  | ANJALI SINHA | 2020-10-17 03:30 | [7 empty] | 1: 3964 - Complete; 2: 36505 - Planned; 3: 95439 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
81152 | WBS.2.2.1.7.1.19 | N | N | Planned | Execute Final Cutover Extracts from ECC - Small | 2.5 | 2020-10-16 18:00 | 2020-10-16 20:30 | 2020-10-16 | ANJALI SINHA | DATA | 3964,3966,3967,3968,36505,95439 | #done |  |  | ANJALI SINHA | 2020-10-17 03:30 | [7 empty] | 1: 3964 - Complete; 2: 3966 - Complete; 3: 3967 - Complete; 4: 3968 - Complete; 5: 36505 - Planned; 6: 95439 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
29567 | WBS.2.2.1.7.22.6 | N | N | Planned | Extract MAP (Moving Average Price values) from ECC for Procured Materials as of cutoff date | 1 | 2020-10-16 18:00 | 2020-10-16 19:00 | 2020-10-16 | ANJALI SINHA | DATA | 36505,95439 | #done |  |  | ANJALI SINHA | 2020-10-17 03:30 | [7 empty] | 1: 36505 - Planned; 2: 95439 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
95506 | WBS.2.2.1.7.1.7 | N | N | Planned | Execute Load program - PTM_C0094 Convert Setup groups / Setup Matrix | 1 | 2020-10-07 07:02 | 2020-10-07 08:02 | 2020-10-07 | PRADEEP CHEEDALLA | DATA | 95507 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-07 16:32 | [7 empty] | 1: 95507 - Planned |  | FALSE | FALSE | TRUE | FALSE
94452 | WBS.2.2.1.7.1.14 | N | N | Planned | PTM_C0201-Extract Storage bins and batches for all sources(PTH,RNC,RVG,SCH,WAU,HTB,BWG) | 2 | 2020-10-16 18:30 | 2020-10-16 20:30 | 2020-10-16 | DEEPA SAW | DATA | 94450,89987 | #done |  |  | DEEPA SAW | 2020-10-17 04:00 | [7 empty] | 1: 94450 - Planned; 2: 89987 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
80928 | WBS.2.2.1.7.13.1 | N | N | Planned | Provide preload file for AS8 MAP (Moving Average Price)/Inventory validation | 2 | 2020-10-16 18:30 | 2020-10-16 20:30 | 2020-10-16 | PRADEEP CHEEDALLA | Data | 29564 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-17 04:00 | [7 empty] | 1: 29564 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
10039 | WBS.2.2.1.7.1.12 | N | N | Planned | PTH - PTM_C0201 - Extract E80 Storage Bins and Batches | 1 | 2020-10-16 18:30 | 2020-10-16 19:30 | 2020-10-16 | DEBRAJ PAL | DATA | 8874,89987 | #done |  |  | DEBRAJ PAL | 2020-10-17 04:00 | [7 empty] | 1: 8874 - Planned; 2: 89987 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
80925 | WBS.2.2.1.6.1.2 | N | N | Planned | Update Material Cross Reference (Xref) due to dual maintenance after initial conversion | 1 | 2020-10-16 18:45 | 2020-10-16 19:45 | 2020-10-16 | DEEPA SAW | DATA | 36505,95428 | #done |  |  | DEEPA SAW | 2020-10-17 04:15 | Material | [6 empty] | 1: 36505 - Planned; 2: 95428 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
80929 | WBS.2.2.1.7.23.10 | N | N | Planned | Provide preload file for ECC MAP (Moving Average Price)/Inventory validation | 2 | 2020-10-16 19:00 | 2020-10-16 21:00 | 2020-10-16 | PRADEEP CHEEDALLA | DATA | 29567 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-17 04:30 | [7 empty] | 1: 29567 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92169 | WBS.2.1.8.2.2.15 | N | N | Planned | Turn OFF DRFOUT in MDG for all Material Updates | 0.25 | 2020-10-16 19:00 | 2020-10-16 19:15 | 2020-10-16 | PHANI GHANTASALA | DATA | 91471,36505,90606,92752 | #start |  |  | PHANI GHANTASALA | 2020-10-17 04:30 | Material | [6 empty] | 1: 91471 - Planned; 2: 36505 - Planned; 3: 90606 - Planned; 4: 92752 - Planned | Yet to receive | TRUE | FALSE | FALSE | FALSE
5698 | WBS.2.2.1.4.3.3 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Transform program - Convert Open Purchase Orders | 3 | 2020-10-19 06:00 | 2020-10-19 09:00 | 2020-10-19 | ANJALI SINHA | DATA | 81155,82626,89675,81154 | #done |  |  | ANJALI SINHA | 2020-10-19 15:30 | Customer | [6 empty] | 1: 81155 - Planned; 2: 82626 - Planned; 3: 89675 - Planned; 4: 81154 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5770 | WBS.2.2.1.7.29.3 | N | N | Planned | ITR_C0067 - Execute Transform program - Convert Scheduled Maintenance Plans – Asset suite | 2 | 2020-10-16 20:30 | 2020-10-19 06:30 | 2020-10-19 | ANKIT AGARWAL | DATA | 81154,5476 | #done |  |  | ANKIT AGARWAL | 2020-10-17 06:00 | [7 empty] | 1: 81154 - Planned; 2: 5476 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5765 | WBS.2.2.1.7.15.2 | N | N | Planned | ITR_C0035 - Execute Transform program - Convert Open Notifications – Asset Suite | 1.5 | 2020-10-16 20:30 | 2020-10-16 22:00 | 2020-10-16 | JASPREET SINGH | DATA | 5395,81154,5438,89987,94400 | #done |  |  | JASPREET SINGH | 2020-10-17 06:00 | [7 empty] | 1: 5395 - Planned; 2: 81154 - Planned; 3: 5438 - Planned; 4: 89987 - Planned; 5: 94400 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
96719 | WBS.2.2.1.7.9.1 | N | N | Planned | RNC - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2020-10-16 17:30 | 2020-10-16 18:30 | 2020-10-16 | ANJALI SINHA | DATA | 36505,68450,96703 | Yet to receive |  |  | ANJALI SINHA | 2020-10-17 03:00 | [7 empty] | 1: 36505 - Planned; 2: 68450 - Planned; 3: 96703 - Planned |  | FALSE | FALSE | FALSE | FALSE
94469 | WBS.2.2.1.7.13.28 | N | N | Planned | PTH and WAU - PTM_C0201 - Execute Transform For AS8 MRO Inventory | 2 | 2020-10-16 20:45 | 2020-10-19 06:45 | 2020-10-19 | DEEPA SAW | Data | 10038,81154,5230,94325 | #done |  |  | DEEPA SAW | 2020-10-17 06:15 | [7 empty] | 1: 10038 - Planned; 2: 81154 - Planned; 3: 5230 - Planned; 4: 94325 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92834 | WBS.2.2.1.7.5.7 | N | N | Planned | Execute Preload ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 1 | 2020-10-16 21:00 | 2020-10-16 22:00 | 2020-10-16 | JASPREET SINGH | DATA | 94412,36505,92877 | #done |  |  | JASPREET SINGH | 2020-10-17 06:30 | [7 empty] | 1: 94412 - Planned; 2: 36505 - Planned; 3: 92877 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92840 | WBS.2.2.1.7.23.17 | N | N | Planned | Execute Preload ITR_C0062.1 Convert Work order history – MP2 | 1 | 2020-10-16 21:00 | 2020-10-16 22:00 | 2020-10-16 | ANKIT AGARWAL | DATA | 94412,36505 | #done |  |  | ANKIT AGARWAL | 2020-10-17 06:30 | [7 empty] | 1: 94412 - Planned; 2: 36505 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5488 | WBS.2.2.1.7.15.1 | N | N | Planned | ITR_C0062 - Execute Load Program - Convert Work Order History - AS8 | 2 | 2020-10-19 08:45 | 2020-10-19 10:45 | 2020-10-19 | ANKIT AGARWAL | DATA | 5487 | #done |  |  | ANKIT AGARWAL | 2020-10-19 18:15 | [7 empty] | 1: 5487 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
96720 | WBS.2.2.1.7.20.3 | N | N | Planned | RVG - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2020-10-16 17:30 | 2020-10-16 18:30 | 2020-10-16 | ANJALI SINHA | DATA | 36505,68450,96704 | Yet to receive |  |  | ANJALI SINHA | 2020-10-17 03:00 | [7 empty] | 1: 36505 - Planned; 2: 68450 - Planned; 3: 96704 - Planned |  | FALSE | FALSE | FALSE | FALSE
96347 | WBS.2.2.1.7.16.5 | N | N | Planned | IM Sites - PTM_C0201 - Execute Transform For ECC IM Inventory | 3 | 2020-10-16 21:30 | 2020-10-19 08:30 | 2020-10-19 | DEEPA SAW | DATA | 81153 | #done |  |  | DEEPA SAW | 2020-10-17 07:00 | [7 empty] | 1: 81153 - Planned |  | FALSE | FALSE | TRUE | FALSE
90407 | WBS.2.2.1.7.27.1 | N | N | Planned | PTH - PTM_C0201 - Execute Transform For Elixir Inventory | 2 | 2020-10-19 06:15 | 2020-10-19 08:15 | 2020-10-19 | DEEPA SAW | DATA | 5231,9091,10038,8874,8864,96703,96704 | #done |  |  | DEEPA SAW | 2020-10-19 15:45 | [7 empty] | 1: 5231 - Planned; 2: 9091 - Planned; 3: 10038 - Planned; 4: 8874 - Planned; 5: 8864 - Planned; 6: 96703 - Planned; 7: 96704 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
94467 | WBS.2.2.1.7.13.2 | N | N | Planned | HBG and BG - PTM_C0201 - Execute Transform For ECC MRO Inventory | 2 | 2020-10-16 21:30 | 2020-10-19 07:30 | 2020-10-19 | DEEPA SAW | DATA | 10038,94323,81153,96572 | #done |  |  | DEEPA SAW | 2020-10-17 07:00 | [7 empty] | 1: 10038 - Planned; 2: 94323 - Planned; 3: 81153 - Planned; 4: 96572 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5486 | WBS.2.2.1.7.23.8 | N | N | Planned | ITR_C0062 - Execute Transform Program - Convert Work Order History - AS8 | 2 | 2020-10-16 22:45 | 2020-10-19 08:00 | 2020-10-19 | ANKIT AGARWAL | DATA | 5393,5398,81155,81706,36505 | #done |  |  | ANKIT AGARWAL | 2020-10-17 08:15 | [7 empty] | 1: 5393 - Planned; 2: 5398 - Planned; 3: 81155 - Planned; 4: 81706 - Planned; 5: 36505 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
91850 | WBS.2.2.1.7.13.32 | N | N | Planned | Execute DQ report to compare PO, Material and PIR units of measure | 1.5 | 2020-10-16 20:30 | 2020-10-16 22:00 | 2020-10-16 | PRADEEP CHEEDALLA | Data | 89675,81152,90972 | #done |  |  | PRADEEP CHEEDALLA | 2020-10-17 06:00 | [7 empty] | 1: 89675 - Planned; 2: 81152 - Planned; 3: 90972 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
10027 | WBS.2.2.1.7.5.4 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Transform program - Service Purchase Orders | 4 | 2020-10-19 06:00 | 2020-10-19 10:00 | 2020-10-19 | ANJALI SINHA | DATA | 81155,82626,89675,81154 | #done |  |  | ANJALI SINHA | 2020-10-19 15:30 | [7 empty] | 1: 81155 - Planned; 2: 82626 - Planned; 3: 89675 - Planned; 4: 81154 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5767 | WBS.2.2.1.7.4.5 | N | N | Planned | ITR_C0035 - Execute Load program - Convert Open Notifications – Asset Suite | 1 | 2020-10-19 06:20 | 2020-10-19 07:20 | 2020-10-19 | JASPREET SINGH | DATA | 5766 | #done |  |  | JASPREET SINGH | 2020-10-19 15:50 | [7 empty] | 1: 5766 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5772 | WBS.2.2.1.7.26.6 | N | N | Planned | ITR_C0067 - Execute Load program - Convert Scheduled Maintenance Plans – Asset suite | 2 | 2020-10-19 07:00 | 2020-10-19 09:00 | 2020-10-19 | ANKIT AGARWAL | DATA | 5771,92152 | #done |  |  | ANKIT AGARWAL | 2020-10-19 16:30 | [7 empty] | 1: 5771 - Planned; 2: 92152 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
29571 | WBS.2.1.10.2.14.7 | N | N | Planned | Load Moving Average Prices for ECC (procured material) | 2 | 2020-10-19 07:00 | 2020-10-19 09:00 | 2020-10-19 | DEBRAJ PAL | DATA | 29569,92152 | #done |  |  | DEBRAJ PAL | 2020-10-19 16:30 | [7 empty] | 1: 29569 - Planned; 2: 92152 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
29570 | WBS.2.2.1.7.18.2 | N | N | Planned | Load Moving Average Prices for AS8 | 6 | 2020-10-19 06:15 | 2020-10-19 12:15 | 2020-10-19 | DEBRAJ PAL | DATA | 29566,92152 | #done |  |  | DEBRAJ PAL | 2020-10-19 15:45 | [7 empty] | 1: 29566 - Planned; 2: 92152 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5684 | WBS.2.2.1.7.13.26 | N | N | Planned | PTM_C0202 - Execute Load program - Convert Truck/Transportation Load Data | 3 | 2020-10-19 08:15 | 2020-10-19 11:15 | 2020-10-19 | ANURAG ANAND | Data | 5218,92152,93004,94329,96651,96749,96750 | #done |  |  | ANURAG ANAND | 2020-10-19 17:45 | [7 empty] | 1: 5218 - Planned; 2: 92152 - Planned; 3: 93004 - Planned; 4: 94329 - Planned; 5: 96651 - Planned; 6: 96749 - Planned; 7: 96750 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
90894 | WBS.2.1.15.30.1.1 | N | N | Planned | Replicate materials with Order UOM updates from MDG to S4 for PO conversion | 0.5 | 2020-10-19 07:00 | 2020-10-19 07:30 | 2020-10-19 | PHANI GHANTASALA | DATA | 90893 | #done |  |  | PHANI GHANTASALA | 2020-10-19 16:30 | [7 empty] | 1: 90893 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
5693 | WBS.2.2.1.15.1.3 | N | N | Planned | PTP_C0005 - Execute Transform program - Convert Open Purchase Orders - ECC | 2 | 2020-10-19 07:30 | 2020-10-19 09:30 | 2020-10-19 | JASPREET SINGH | DATA | 81152,89675,90894,90972,91849 | #done |  |  | JASPREET SINGH | 2020-10-19 17:00 | Material | [6 empty] | 1: 81152 - Planned; 2: 89675 - Planned; 3: 90894 - Planned; 4: 90972 - Planned; 5: 91849 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92838 | WBS.2.2.1.7.22.12 | N | N | Planned | Execute Load ITR_C0062.1 Convert Work order history – MP2 | 1 | 2020-10-19 08:00 | 2020-10-19 09:00 | 2020-10-19 | ANKIT AGARWAL | DATA | 92839 | #done |  |  | ANKIT AGARWAL | 2020-10-19 17:30 | [7 empty] | 1: 92839 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92832 | WBS.2.2.1.7.4.11 | N | N | Planned | Execute Load ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 1 | 2020-10-19 08:00 | 2020-10-19 09:00 | 2020-10-19 | JASPREET SINGH | DATA | 92833 | #done |  |  | JASPREET SINGH | 2020-10-19 17:30 | [7 empty] | 1: 92833 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
94486 | WBS.2.2.1.7.23.1 | N | N | Planned | SCH - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2020-10-19 09:45 | 2020-10-19 14:45 | 2020-10-19 | DEBRAJ PAL | DATA | 68398,92152,94479 | #done |  |  | DEBRAJ PAL | 2020-10-19 19:15 | [7 empty] | 1: 68398 - Planned; 2: 92152 - Planned; 3: 94479 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
94599 | WBS.2.2.1.7.1.13 | N | N | Planned | WAU - PTM_C0201 - Execute Load for SAP-WM FG/SFG Inventory | 2 | 2020-10-19 10:15 | 2020-10-19 12:15 | 2020-10-19 | DEBRAJ PAL | DATA | 94597 | Yet to receive |  |  | DEBRAJ PAL | 2020-10-19 19:45 | [7 empty] | 1: 94597 - Planned | Yet to receive |  |  |  | FALSE
96666 | WBS.2.2.1.7.1.15 | N | N | Planned | SAT - PTM_C0201 - Execute Load program for SAT SAP IM (ECC) Inventory | 3 | 2020-10-19 11:30 | 2020-10-19 14:30 | 2020-10-19 | VENKATESH GANESHAN | DATA | 96665 | #done |  |  | VENKATESH GANESHAN | 2020-10-19 21:00 | [7 empty] | 1: 96665 - Planned |  | FALSE | FALSE | TRUE | FALSE
90147 | WBS.2.1.15.30.1.1 | N | N | Planned | Replicate materials with EP/Production SLOC & Frozen Horizon updates from MDG to S4 | 3 | 2020-10-19 11:45 | 2020-10-19 14:45 | 2020-10-19 | PHANI GHANTASALA | DATA | 90038,90068,90851,92742,94725 | #done |  |  | PHANI GHANTASALA | 2020-10-19 21:15 | [7 empty] | 1: 90038 - Planned; 2: 90068 - Planned; 3: 90851 - Planned; 4: 92742 - Planned; 5: 94725 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
96670 | WBS.2.2.1.7.8.1 | N | N | Planned | REX - PTM_C0201 - Execute Load program for REX SAP IM (ECC) Inventory | 3 | 2020-10-19 11:30 | 2020-10-19 14:30 | 2020-10-19 | VENKATESH GANESHAN | DATA | 96669 | #done |  |  | VENKATESH GANESHAN | 2020-10-19 21:00 | [7 empty] | 1: 96669 - Planned |  | FALSE | FALSE | TRUE | FALSE
8883 | WBS.2.2.1.7.23.2 | N | N | Planned | PTH - PTM_C0201 - Execute Load program for Elixir Inventory | 5 | 2020-10-19 11:00 | 2020-10-19 16:00 | 2020-10-19 | DEBRAJ PAL | DATA | 5671,68398,92152,93138,93321 | Yet to receive |  |  | DEBRAJ PAL | 2020-10-19 20:30 | [7 empty] | 1: 5671 - Planned; 2: 68398 - Planned; 3: 92152 - Planned; 4: 93138 - Planned; 5: 93321 - Planned | Yet to receive |  |  |  | FALSE
89764 | WBS.2.2.1.7.20.11 | N | N | Planned | PTP_C0005.1 - AS8 - Turn on the enhancement | 0.5 | 2020-10-19 13:00 | 2020-10-19 13:30 | 2020-10-19 | PHANI GHANTASALA | DATA | 10028,82656 | Yet to receive |  |  | PHANI GHANTASALA | 2020-10-19 22:30 | [7 empty] | 1: 10028 - Planned; 2: 82656 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
10029 | WBS.2.2.1.7.20.5 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Load program - Service Purchase Orders | 2 | 2020-10-19 13:00 | 2020-10-19 15:00 | 2020-10-19 | PHANI GHANTASALA | DATA | 10028,82656,82766,92152 | Yet to receive |  |  | PHANI GHANTASALA | 2020-10-19 22:30 | [7 empty] | 1: 10028 - Planned; 2: 82656 - Planned; 3: 82766 - Planned; 4: 92152 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
5700 | WBS.2.2.1.7.13.30 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Load program - Convert Open Purchase Orders | 6 | 2020-10-19 13:00 | 2020-10-19 19:00 | 2020-10-19 | PHANI GHANTASALA | Data | 5699,82657,82766,92152 | Yet to receive |  |  | PHANI GHANTASALA | 2020-10-19 22:30 | [7 empty] | 1: 5699 - Planned; 2: 82657 - Planned; 3: 82766 - Planned; 4: 92152 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
94491 | WBS.2.2.1.7.13.33 | N | N | Planned | HBG - PTM_C0201 - Execute Load program for ECC Inventory (MRO) | 3 | 2020-10-19 11:00 | 2020-10-19 14:00 | 2020-10-19 | DEBRAJ PAL | Data | 94471,92152,29567,29571,93904 | Yet to receive |  |  | DEBRAJ PAL | 2020-10-19 20:30 | [7 empty] | 1: 94471 - Planned; 2: 92152 - Planned; 3: 29567 - Planned; 4: 29571 - Planned; 5: 93904 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
97173 | WBS.2.2.1.15.1.5 | N | N | Planned | BG (FG/PR) AND WAU (FG) - PTM_C0201 - Execute Transform for SAP-WM Inventory | 2.5 | 2020-10-19 06:15 | 2020-10-19 08:45 | 2020-10-19 | DEEPA SAW | DATA | 10038,9091,96571 | #done |  |  | DEEPA SAW | 2020-10-19 15:45 | Customer | [6 empty] | 1: 10038 - Planned; 2: 9091 - Planned; 3: 96571 - Planned |  | FALSE | FALSE | TRUE | FALSE
94492 | WBS.2.2.1.7.29.1 | N | N | Planned | WAU - PTM_C0201 - Execute Load program for AS8 Inventory (MRO) | 4 | 2020-10-19 15:15 | 2020-10-19 19:15 | 2020-10-19 | DEBRAJ PAL | DATA | 29564,29570,94472,92152,94764 | #done |  |  | DEBRAJ PAL | 2020-10-20 00:45 | [7 empty] | 1: 29564 - Planned; 2: 29570 - Planned; 3: 94472 - Planned; 4: 92152 - Planned; 5: 94764 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
94493 | WBS.2.2.1.7.26.2 | N | N | Planned | PTH - PTM_C0201 - Execute Load program for AS8 Inventory (MRO) | 4 | 2020-10-19 15:15 | 2020-10-19 19:15 | 2020-10-19 | DEBRAJ PAL | DATA | 29564,29570,68331,94473,92152 | #done |  |  | DEBRAJ PAL | 2020-10-20 00:45 | [7 empty] | 1: 29564 - Planned; 2: 29570 - Planned; 3: 68331 - Planned; 4: 94473 - Planned; 5: 92152 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5695 | WBS.2.2.1.7.13.36 | N | N | Planned | PTP_C0005 - Execute Load program - Convert Open Purchase Orders - ECC | 3 | 2020-10-19 14:45 | 2020-10-19 17:45 | 2020-10-19 | JASPREET SINGH | Data | 5694,82646,82766,92152,82340,90147 | Yet to receive |  |  | JASPREET SINGH | 2020-10-20 00:15 | [7 empty] | 1: 5694 - Planned; 2: 82646 - Planned; 3: 82766 - Planned; 4: 92152 - Planned; 5: 82340 - Planned; 6: 90147 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
96689 | WBS.2.2.1.7.16.5 | N | N | Planned | BG (FG/SFG) - PTM_C0201 - Execute Load for SAP-WM FG/SFG Inventory | 2 | 2020-10-19 10:45 | 2020-10-19 12:45 | 2020-10-19 | VENKATESH GANESHAN | DATA | 96688,96565 | Yet to receive |  |  | VENKATESH GANESHAN | 2020-10-19 20:15 | [7 empty] | 1: 96688 - Planned; 2: 96565 - Planned |  |  |  |  | FALSE
89763 | WBS.2.2.1.7.21.5 | N | N | Planned | PTP_C0005.1 - AS8 - Turn off the enhancement | 0.5 | 2020-10-19 21:45 | 2020-10-20 06:15 | 2020-10-20 | PHANI GHANTASALA | DATA | 10029,5696,10030 | Yet to receive |  |  | PHANI GHANTASALA | 2020-10-20 07:15 | [7 empty] | 1: 10029 - Planned; 2: 5696 - Planned; 3: 10030 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
9657 | WBS.2.2.1.7.9.3 | N | N | Planned | PTP_C0236 - Execute Transform program - Convert Goods Receipt for Open Invoice Reconciliation | 1 | 2020-10-20 06:45 | 2020-10-20 07:45 | 2020-10-20 | ANURAG ANAND | DATA | 80747,82480,5701,5696,82661,82652,94291 | Yet to receive |  |  | ANURAG ANAND | 2020-10-20 16:15 | [7 empty] | 1: 80747 - Planned; 2: 82480 - Planned; 3: 5701 - Planned; 4: 5696 - Planned; 5: 82661 - Planned; 6: 82652 - Planned; 7: 94291 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
90896 | WBS.2.2.1.7.13.11 | N | N | Planned | Replicate materials after reverting order UOM and AUOM updates from MDG to S4 | 5 | 2020-10-20 06:45 | 2020-10-20 11:45 | 2020-10-20 | PHANI GHANTASALA | Data | 90895 | #done |  |  | PHANI GHANTASALA | 2020-10-20 16:15 | [7 empty] | 1: 90895 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
9659 | WBS.2.2.1.7.8.3 | N | N | Planned | PTP_C0236 - Execute Load program - Convert Goods Receipt for Open Invoice Reconciliation | 1 | 2020-10-20 11:15 | 2020-10-20 12:15 | 2020-10-20 | ANURAG ANAND | DATA | 9658,68402,80748,5696,5701,68331,92152,95281,94779,94780,94782,94783,94777,96645,96646 | #done |  |  | ANURAG ANAND | 2020-10-20 20:45 | [7 empty] | 9658 - Planned | 68402 - Planned | 80748 - Planned | 5696 - Planned | 5701 - Planned | 68331 - Planned | 92152 - Planned | 95281 - Planned | 94779 - Planned | 94780 - Planned | 94782 - Planned | 94783 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92172 | WBS.2.2.1.7.13.12 | N | N | Planned | Turn ON DRFOUT in MDG after All Material Updates | 0.25 | 2020-10-20 11:45 | 2020-10-20 12:00 | 2020-10-20 | PHANI GHANTASALA | Data | 90894,90895,90896 | #done |  |  | PHANI GHANTASALA | 2020-10-20 21:15 | [7 empty] | 1: 90894 - Planned; 2: 90895 - Planned; 3: 90896 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
92396 | WBS.2.1.9.28.1.3 | N | N | Planned | Check for Material Change Requests and Manually Updated Materials that may not have Replicated Downstream | 1 | 2020-10-20 12:00 | 2020-10-20 13:00 | 2020-10-20 | SHANKAR RAMNARAYANAN | DATA | 92172,95766 | #done |  |  | SHANKAR RAMNARAYANAN | 2020-10-20 21:30 | [7 empty] | 1: 92172 - Planned; 2: 95766 - Planned | Yet to receive | FALSE | FALSE | TRUE | FALSE
9661 | WBS.2.2.1.7.27.3 | N | N | Planned | PTP_C0237 - Execute Transform program - Convert Goods Receipt Inventory Adjustment | 1 | 2020-10-20 14:30 | 2020-10-20 15:30 | 2020-10-20 | ANURAG ANAND | DATA | 82361,82481,36505 | Yet to receive |  |  | ANURAG ANAND | 2020-10-21 | [7 empty] | 1: 82361 - Planned; 2: 82481 - Planned; 3: 36505 - Planned | Yet to receive | FALSE | FALSE | FALSE | FALSE
9663 | WBS.2.2.1.7.23.9 | N | N | Planned | PTP_C0237 - Execute Load program - Convert Goods Receipt Inventory Adjustment | 2 | 2020-10-20 17:30 | 2020-10-20 19:30 | 2020-10-20 | ANURAG ANAND | DATA | 9662,9660,92152 | #start |  |  | ANURAG ANAND | 2020-10-21 03:00 | [7 empty] | 1: 9662 - Planned; 2: 9660 - Planned; 3: 92152 - Planned | Yet to receive | TRUE | FALSE | FALSE | FALSE
8788 | WBS.2.2.1.7.13.4 | N | N | Planned | PTM_C0080 - Execute Transform - Convert Costing BOMs | 2 | 2020-11-02 06:30 | 2020-11-02 08:30 | 2020-11-02 | PRADEEP CHEEDALLA | DATA | 7882 | Yet to receive |  |  | PRADEEP CHEEDALLA | 2020-11-02 16:00 | [7 empty] | 1: 7882 - Planned | Yet to receive |  |  |  | FALSE
8790 | WBS.2.2.1.7.18.4 | N | N | Planned | PTM_C0082 - Execute Preload - Convert Costing Routing (Simulation Mode) | 1 | 2020-11-02 06:45 | 2020-11-02 07:45 | 2020-11-02 | ANURAG ANAND | DATA | 7883 | Yet to receive |  |  | ANURAG ANAND | 2020-11-02 16:15 | [7 empty] | 1: 7883 - Planned | Yet to receive |  |  |  | FALSE
8792 | WBS.2.1.15.17.1.8 | N | N | Planned | PTM_C0082 - Execute Load program - Costing Routing | 1 | 2020-11-02 08:00 | 2020-11-02 09:00 | 2020-11-02 | ANURAG ANAND | DATA | 8791 | Yet to receive |  |  | ANURAG ANAND | 2020-11-02 17:30 | [7 empty] | 1: 8791 - Planned | Yet to receive |  |  |  | FALSE
5190 | WBS.2.2.1.7.11.13 | N | N | Planned | PTM_C0080 - Execute Load in S/4HANA - for Costing BOMS | 3 | 2020-11-02 09:00 | 2020-11-02 12:00 | 2020-11-02 | PRADEEP CHEEDALLA | DATA | 8789 | Yet to receive |  |  | PRADEEP CHEEDALLA | 2020-11-02 18:30 | [7 empty] | 1: 8789 - Planned | Yet to receive |  |  |  | FALSE
8797 | WBS.2.2.1.7.15.4 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Costing Production Versions (Simulation Mode) | 2 | 2020-11-02 14:00 | 2020-11-02 16:00 | 2020-11-02 | ANKIT AGARWAL | DATA | 7886 | Yet to receive |  |  | ANKIT AGARWAL | 2020-11-02 23:30 | [7 empty] | 1: 7886 - Planned | Yet to receive |  |  |  | FALSE
8799 | WBS.2.2.1.7.16.5 | N | N | Planned | PTM_C0085 - Execute Load Program - Convert Costing Production Versions | 1 | 2020-11-02 16:15 | 2020-11-03 01:15 | 2020-11-03 | PHANI GHANTASALA | DATA | 8798 | Yet to receive |  |  | PHANI GHANTASALA | 2020-11-03 01:45 | [7 empty] | 1: 8798 - Planned | Yet to receive |  |  |  | FALSE
96682 | WBS.2.2.1.7.16.5 | N | N | Planned | BG - PTM_C0201 - Execute Load program for ECC Inventory (MRO) | 3 | 2020-10-19 12:00 | 2020-10-19 15:00 | 2020-10-19 | DEBRAJ PAL | DATA | 96681,92152,29567,29571,96631 | #done |  |  | DEBRAJ PAL | 2020-10-19 21:30 | [7 empty] | 1: 96681 - Planned; 2: 92152 - Planned; 3: 29567 - Planned; 4: 29571 - Planned; 5: 96631 - Planned |  | FALSE | FALSE | TRUE | FALSE
94476 | WBS.2.2.1.7.16.5 | N | N | Planned | PTH - PTM_C0201 - Execute preload for E80 Inventory Load file (FG) | 1 | 2020-10-19 06:15 | 2020-10-19 07:15 | 2020-10-19 | DEBRAJ PAL | DATA | 9091,10038,8864,10039 | #done |  |  | DEBRAJ PAL | 2020-10-19 15:45 | [7 empty] | 1: 9091 - Planned; 2: 10038 - Planned; 3: 8864 - Planned; 4: 10039 - Planned |  | FALSE | FALSE | TRUE | FALSE
94478 | WBS.2.2.1.7.16.5 | N | N | Planned | PTH - PTM_C0201 - Execute Load for E80 FG Inventory | 1 | 2020-10-19 07:45 | 2020-10-19 08:45 | 2020-10-19 | DEBRAJ PAL | DATA | 94477 | Yet to receive |  |  | DEBRAJ PAL | 2020-10-19 17:15 | [7 empty] | 1: 94477 - Planned |  |  |  |  | FALSE
96728 | WBS.2.2.1.7.16.5 | N | N | Planned | RNC - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2020-10-19 09:45 | 2020-10-19 14:45 | 2020-10-19 | DEBRAJ PAL | DATA | 96727,68398,92152 | #done |  |  | DEBRAJ PAL | 2020-10-19 19:15 | [7 empty] | 1: 96727 - Planned; 2: 68398 - Planned; 3: 92152 - Planned |  | FALSE | FALSE | TRUE | FALSE
96735 | WBS.2.2.1.7.16.5 | N | N | Planned | RVG - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2020-10-19 09:45 | 2020-10-19 14:45 | 2020-10-19 | DEBRAJ PAL | DATA | 96734,68398,92152 | #done |  |  | DEBRAJ PAL | 2020-10-19 19:15 | [7 empty] | 1: 96734 - Planned; 2: 68398 - Planned; 3: 92152 - Planned |  | FALSE | FALSE | TRUE | FALSE